Annex 1 – tender Specifications

Survey on the access to finance of small and medium-sized enterprises (SAFE)

Table of contents

1.	Subject of the survey	3

1.1	General features	3

1.2	General contractor requirements	4

2.	Specifications; Deliverables	5

2.1	Definition of the universe	5

2.1.1	Countries to be covered	5

2.1.2	Universe	7

2.2	Sampling	8

2.2.1	Representativeness of the sample	8

2.2.2	Selection of the sample – sampling frame	8

2.2.3	Sample sizes	8

2.2.4	Response rate	9

2.3	Panel component	9

2.4	Interviewing technique and organisation	9

2.4.1	Introduction	9

2.4.2	Other survey modes	10

2.4.3	Language of interviewing	10

2.4.4	Fieldforce	11

2.4.5	Conduct of fieldwork	12

2.5	Questionnaire	12

2.5.1	Calculation of question units and length of questionnaire	12

2.5.2	Design, update, and translation of the questionnaire	14

2.6	Data processing: coding, cleaning, weighting	15

2.6.1	At the level of the members of the network	15

2.6.2	At the level of the coordination centre	15

2.6.3	Weighting	15

2.7	Organisation and timetable	16

2.7.1	Organisation of a wave of the SAFE by the ECB and/or the EC and the contractor	16

2.7.2	Organisation of the survey by the contractor	17

2.8	Reports and documents – delivery, distribution and archiving	17

2.8.1	Questionnaires, raw data (both initial and final), data analysis and technical report	17

2.8.2	Written reports	21

2.8.3	SAFE seminar	22

2.8.4	Archiving and publication	22

2.9	Quality control	22

2.9.1	Controls realised by the members of the network and the coordination centre within the framework of the SAFE	22

2.9.2	Controls realised by the ECB, the EC or their representatives	23

2.10	Method for calculating the cost of a survey	23

3.	Documentation for tenderers	24

4.	On site visits	24

5.	Additional specifications and documentation	25

5.1	Questionnaires	25

5.1.1	Current questionnaire for ECB waves	25

5.1.2	Current questionnaire for Common waves	32

5.2	Raw data files format	42

5.3	Sample data for the volume tables	42

5.3.1	Table A	43

5.3.2	Table B	43

5.4	Sample sizes	44

5.4.1	ECB waves	44

5.4.2	Common waves	44

5.5	Price tables	45

5.5.1	ECB waves	45

5.5.2	Common waves	47

5.5.3	Other items to be priced	48

5.5.4	Reference price	49

5.6	Timetable of the survey	49

# Subject of the survey

## General features

The Survey on the Access to Finance of small and medium-sized Enterprises (SAFE) is a qualitative survey of firms (see specification of the universe in section 2.1 below). The purpose is to provide regular information on the financing conditions of small and medium-sized enterprises (SMEs), as well as larger firms, in a certain number of countries.

The general features outlined in this section are only indicate and are described in detail in section 2 below.

The survey shall be run in two different compositions:

- Every six months (excepting when the Common wave described below is run), in the euro area but excluding some countries (as of 1 January 2010, the 5 smallest countries of the euro area where excluded). These waves are known as “ECB waves” and the requesting institution is the ECB.

- Every two years, in all countries of the European Union plus some additional requested countries in the rest of the world (see section 2.1.1 below). These waves are known as “Common waves”, and the requesting institutions are both the ECB and the EC. Separate specific contracts will be signed with the contractor by both institutions, but they are both part of the same survey.

In both types of waves, all firms shall be asked a common set of questions (Common questions) with approximately 30 question-units (see section 5.1 for the different sets of questions, and section 2.5.1 for the definition of question-units). In Common waves, firms shall then receive either or both of two sets of questions (ECB questions and Commission questions). Firms receiving only the ECB questions (in addition to the Common questions) shall form the “ECB component”; firms receiving only the Commission questions (in addition to the Common questions) shall form the “Commission component”; firms receiving both the ECB and Commission questions shall form the “Common component”.

In ECB waves, all firms shall then receive ECB questions.

The following table shall be an indication only. The ECB and/or the EC may adapt the exact structure of the waves for each specific contract ordered in accordance with the Contract.

Table 1: Common waves

| Component | Countries | Questions |
| --- | --- | --- |
| Commission | Countries not in the euro area | Common, Commission |
| Common | All euro area countries | Common, Commission, |
|  |  | ECB |
| ECB | Germany, France, Spain, Italy, Portugal, Netherlands | Common, ECB |

Table 2: ECB waves

| Component | Countries | Questions |
| --- | --- | --- |
| ECB | Euro area countries, excluding the five smallest | Common, ECB |

Two waves of this survey have been conducted in 2009, one Common and one ECB. The documentation on these waves is available on the websites of the ECB and of the EC (DG Enterprise and Industry).

The SAFE may be conducted by telephone, fax, internet, or a combination of these methods, as indicated in section 2.4.

## General contractor requirements

The contractor must at least fulfil the selection criteria and minimum capacity levels set out in Chapter IV, section 4 of the ITT and must provide the information and documents listed in the Tender Submission Form (Annex 3).

In particular, the contractor must have a coordination centre and a network of polling institutes covering all the countries and territories involved. The contractor may also act directly as coordination centre. The polling institutes will be referred to hereinafter as “members of the network”. The members of the network must be organised into an integrated network. The aim of the EC and the ECB is to have access to a sound and experienced network. Therefore, tenderers shall include the contact details, experience and precise qualifications of the coordination centre and the members of the network. The coordination centre and the members of the network shall remain unchanged for the duration of the Contract. Any change is subject to the procedure set out in the Contract.

The successful tenderer will be fully responsible for all aspects (technical, economic, financial and legal) of the Contract as well as the specific contracts signed with the ECB and/or the EC. The working language for the Contract shall be English.

The coordination centre shall be the sole technical partner with which the ECB will deal for implementing the SAFE and shall provide the ECB and/or the EC with all the requisite methodological advice and shall ensure the consistency of the methods and procedures applied in the various countries and compliance with the specifications below.

# Specifications; Deliverables

These specifications describe the methodology as regards:

2.1	Definition of the universe

2.2	Sampling

2.3	Panel component

2.4	Interviewing technique and organisation

2.5	Questionnaire

2.6	Data processing: coding, cleaning, weighting

2.7	Organisation and timetable

2.8	Reports and documents – delivery, distribution and archiving

2.9	Quality control

2.10	Method for calculating the cost of a survey

## Definition of the universe

### Countries to be covered

For the Common waves the core list of countries is composed of the countries in Table 3:

Table 3: List of core countries

| Austria | Belgium | Bulgaria | Croatia |
| --- | --- | --- | --- |
| Cyprus | Czech Republic | Denmark | Estonia |
| Finland | France | Germany | Greece |
| Hungary | Iceland | Ireland | Italy |
| Latvia | Lithuania | Luxembourg | Malta |
| Netherlands | Norway | Poland | Portugal |
| Romania | Slovakia | Slovenia | Spain |
| Sweden | Turkey | United Kingdom |  |

All surveys to be performed by the contractor must be able to cover these 31 core countries. A member of the network may cover one or more countries. However, a single network member may not cover more than four countries.

The ECB and/or the EC may decide not to include all core countries in the Common waves and that some non-European Union countries may be excluded from the sample for the Common waves. Such decision shall be taken before each such wave in accordance with the order procedure set out in the Contract.

Optionally, for the Common waves, and upon the instruction of the ECB and/or the EC as defined in the order procedure set out in the Contract, the countries listed in Table 4 shall be added to the list of countries to be covered by the survey. Although they are not a requirement of the survey, coverage of these countries would be considered an asset for the tenderers.

Table 4: List of supplementary countries

| Liechtenstein | Switzerland | Former Yugoslav Republic of Macedonia |
| --- | --- | --- |
| Serbia | Montenegro |  |
| Israel | Albania |  |

For the ECB waves, at the time of the initiation of the tender, the countries in the euro area are listed in Table 5:

Table 5: List of euro area countries (in 2010)

| Austria | Belgium | Republic of Cyprus | Finland |
| --- | --- | --- | --- |
| France | Germany | Greece | Ireland |
| Italy | Luxembourg | Malta | Netherlands |
| Portugal | Slovakia | Slovenia | Spain |

The ECB reserves the right to add additional countries from the core list of countries in Table 3 to the ECB waves, in particular to cover for the expansion of the euro area, or for any other reason.

The ECB may decide not to include all countries in the ECB waves. The following countries may be excluded from the sample for the ECB waves, as decided and communicated by the ECB before each such wave in accordance with the order procedure set out in the Contract. The list of currently excluded countries is given in Table 6.

Table 6: List of countries excluded from the ECB waves

| Cyprus | Luxembourg | Malta |
| --- | --- | --- |
| Slovakia | Slovenia |  |

### Universe

The universe of the survey is non-financial companies having at least one employee, which are active in any of the countries covered by the survey and have market or for-profit activities, excluding the following sectors: agriculture, fishing, financial sector, public administration, health, social work activities, education, activities of households, and extraterritorial organizations and bodies.

The following sections of the NACE rev. 2 shall be covered:

B	Mining and quarrying

C	Manufacturing

D	Electricity, gas, steam, and air conditioning supply

E	Water supply, sewerage, waste management and remediation activities

F	Construction

G 	Wholesale and retail trade; repair of motor vehicles and motorcycles

H 	Transportation and storage

J	Information and communication

L	Real estate activities

M	Professional, scientific and technical activities

N	Administrative and support service activities

R	Arts, entertainment and recreation

S	Other services activities

For the purposes of the survey, these sections are grouped into Industry (B to E), Construction (F), Trade (G) and Services (H to S).

The statistical unit shall be the enterprise and the respondent shall be the owner, the chief financial officer, the head accountant or the most financially knowledgeable employee of the firm. Tenderers shall indicate how they will ensure that the correct person is interviewed.

## Sampling

### Representativeness of the sample

For each country covered by the SAFE, samples (either Common and Commission component together, or Common and ECB component together) must be representative of the universe. Coverage of the whole territory of each country is not a requirement in the case of the French overseas departments, the Canaries, Madeira and the Azores. However, tenderers must indicate whether or not they will cover these territories.

Members of the network shall be responsible for the representativeness of their sample on the basis of the instructions of the ECB and/or the EC. They must apply weightings to establish maximum representativeness. The coordination centre shall check the representativeness of each national sample. However, in case the sampling frame (see next section) is a homogeneous source across several countries, the coordination centre may be responsible for the representativeness of the sample in these countries.

### Selection of the sample – sampling frame

The sample shall be a probabilistic sample, stratified by country, size of firm, and main economic activity. If the sample is too small to allow this stratification, the stratification shall be done by country and size of firm.

Tenderers must specify, for each country, the sources and bases which they will use to put the samples together and their sampling methods. Tenderers must detail the coverage of the sample with respect to the target population and its representativity of the universe, in particular for the smallest firms (less than 10 employees) as well as for newly created firms. Homogeneous sources across the maximum number of countries are preferred.

Tenderers shall also specify the auxiliary information available from the sampling frame, which could be used for the analysis, for example but not limited to, legal form of the firm, detailed sector in NACE classification, balance sheet information, and number of employees or size class.

### Sample sizes

Sample sizes will depend on the size of the countries. Any country sample shall have a minimum of 100 interviews and a maximum of 1,500 interviews.  As an indication only, the sample sizes for the waves carried out in 2009 are as follows:

Germany, France, Italy, Spain	1,000 interviews

United Kingdom	500 interviews

Netherlands, Portugal, Poland, Turkey	300 interviews

Austria, Belgium, Bulgaria, Czech Republic, Denmark, Hungary, Romania, Sweden	200 interviews

Croatia, Cyprus, Estonia, Finland, Iceland, Ireland, Latvia, Lithuania, Luxembourg, Malta, Norway, Slovakia, Slovenia 	100 interviews

In accordance with the order procedure set out in the Contract, the ECB and/or the EC shall determine which countries shall be covered for each wave of the survey, and for each of those countries, the number of completed interviews to be achieved.

### Response rate

Tenderers must set out in detail the specific method which they intend to use to ensure that the response rate for the survey is as high as possible.

## Panel component

To obtain more accurate estimators for semester-to-semester changes, the ECB waves shall have a rotating panel of firms. Panel recruitment shall thus be specific to euro area countries included in the ECB waves (excluding the smallest countries). All firms participating in an ECB wave shall be included in the panel component for a determined number of waves. Firms in the panel must be drawn from a probabilistic sample as described in section 2.2; pre-existing panel or focus group of firms may not be used. The ECB shall provide the contractor with the contact details of the firms already participating in the panel before the beginning of the first wave. The coordination centre and the members of the network may not use the panel of firms for any survey not requested by the ECB.

Micro firms shall be followed during 4 consecutive semesters (i.e. 4 waves) before being replaced by new firms. Small and medium-sized firms shall be followed for 6 consecutive semesters. Large firms shall be followed for 12 consecutive semesters. In other words, 1/4th of the micro firms, 1/6th of the small and medium-sized, and 1/12th of the large firms shall be replaced in every wave. Firms included in the panel shall be traced through their identifier from wave to wave, and tenderers shall specify the management of the panel.

Tenderers shall specify the means they will employ to ensure the highest possible participation rate of firms in the panel and the procedures they will use to recruit firms in the panel. The causes of attrition shall be followed firm by firm and shall be reported to the ECB. In case a firm drops out of the panel before its specified number of waves, for each country in the euro area, tenderers shall indicate how they will ensure that the sample drawn will remain representative of the universe.

## Interviewing technique and organisation

### Introduction

The primary way of contacting firms not previously interviewed shall be the telephone. Surveys shall in that case be conducted primarily using computer-assisted telephone interviewing (CATI).

For the purposes of this tender procedure, the concept of telephone interviewing covers fixed and mobile telephony.

The following information must be provided for each country and for each member of the network:

- the CATI system used;

- the number of contacts made before cutting off.

The interviews for the survey must be conducted as far as possible during the usual opening hours of businesses in the respective country. Tenderers shall indicate for each country the periods of the year when interviews will not be possible (for example public holidays, Christmas period) or when interviews may be difficult (for example when companies have to close the accounts, or for summer holidays).

Tenderers shall assess the situation of firms as regards the possession of a fixed land line and of mobile phone lines, and should specify the measures (if any) intended to address this situation.

### Other survey modes

In order to increase the response rate, tenderers shall describe how the use of other modes might improve the participation of firms in the survey.

In connection with the panel component in particular, some firms may be more eager to participate in the repeated waves through the internet. Tenderers shall describe how they would put in place such a system and what impact it may have on costs, quality, and timeliness of the survey.

### Language of interviewing

For each country involved, interviews shall be conducted in at least the languages listed in Table 7.

Table 7: List of languages to be covered by country

| Country | Languages |  | Country | Languages |
| --- | --- | --- | --- | --- |
| Austria | German |  | Bulgaria | Bulgarian |
| Belgium | French & Dutch |  | Croatia | Croatian |
| Cyprus | Greek |  | Denmark | Danish |
| Czech Republic | Czech |  | Estonia | Estonian |
| Finland | Finnish & Swedish |  | Germany | German |
| France | French |  | Greece | Greek |
| Hungary | Hungarian |  | Ireland | English & Irish |
| Iceland | Icelandic |  | Italy | Italian |
| Latvia | Latvian |  | Luxembourg | French & German |
| Lithuania | Lithuanian |  | Malta | Maltese & English |
| Netherlands | Dutch |  | Poland | Polish |
| Norway | Norwegian |  | Portugal | Portuguese |
| Romania | Romanian |  | Slovenia | Slovenian |
| Slovakia | Slovakian |  | Spain | Spanish |
| Sweden | Swedish |  | Turkey | Turkish |
| United Kingdom | English |  |  |  |

Tenderers shall also indicate which languages they will cover for the 7 additional countries referred to in Table 4.

### Fieldforce

#### Size and experience

Each member of the interviewing team covering a given country must have at least two months' survey experience, speak national language (see supra) at native speaker’s level and possess either by academic background, residence or professional experience a deep knowledge of the country where the interview takes place..

The fieldforce covering each country must comprise at least 5 people, and at least 15 people for Germany, France, Spain and Italy.

The stability of the team of interviewers has an impact on the quality of the survey. Tenderers must provide the turnover of the interviewing team (number of persons joining the team over a year, divided by the number of staff at the beginning of the year) for each country and for the most recent period available.

Tenderers must indicate for each country and for each interview language the size of the fieldforce that will be used for the SAFE, with the samples indicated for the Common waves in section 5.4.2.

They shall also indicate the size and location of the CATI fieldforce available for each language.

#### Briefing of the interviewers

In all countries, fieldwork shall be conducted on the basis of detailed and uniform instructions prepared by the coordination centre, with possible indications by the ECB and/or the EC in accordance with the order procedure set out in the Contract.

The contractor must as a minimum provide written instructions to the interviewers for the conduct of the interviews.

Tenderers must outline the briefing methods they will use for the SAFE and the content of these briefings.

#### Control

The contractor shall ensure that control procedures cover at least 8% of the interviews carried out. Tenderers shall describe, for each member of the network, the measures, in particular the types and frequency of checks, used to ensure the quality of their services, specifying for each country the percentage of interviews which will be checked; and the control method for each type of survey (CATI/internet).

#### Changing a member of the network

If a member of the network fails to comply substantially or repeatedly with deadlines and/or to meet the necessary quality, the ECB, after having liaised with the EC, may request the contractor to suspend the member’s participation in SAFE in accordance with the procedure set out in the Contract.

In any such event, (a) the contractor must provide the ECB with detailed proposals for the replacement of the network member concerned; (b) the future network member proposed as a replacement must conduct a pilot survey of SMEs at his own expense, containing the D questions (demographic) and questions Q0, Q3, Q5 and Q6 (see section 5.1.1) for a sample of 100 respondents; and (c) the results of the pilot survey must be submitted to the ECB, which will take the final decision and inform the contractor of that decision by registered mail. To take part in the network, the member thus selected must also meet the selection criteria listed in Chapter IV of the ITT.

### Conduct of fieldwork

Tenderers shall indicate how updates of the fieldwork will be given to the ECB and/or EC during the fieldwork process. Information on the number of completed interviews shall be given at least every week, by country. Raw data –non edited– shall be submitted every two weeks to the ECB and/or the EC.

## Questionnaire

The questionnaire to be used every six months for the ECB waves is available in section 5.1.1. The ECB may introduce changes to the questionnaire between waves in accordance with the order procedure set out in the Contract, either in the wording of the questions, the explanatory elements, or in the number of questions, although the objective shall be to track changes in specific behaviours and opinions from semester to semester. Changes to the number of questions will affect the price of the survey according to the methodology described in section 2.10, and will take place according to the timing described in section 2.7.

The questionnaire to be used every two years (in its different forms) for the Common waves is available in section 5.1.2. It includes most of the questionnaire used for the ECB waves. The questions may be modified or deleted by the ECB and/or EC in accordance with the order procedure set out in the Contract, and new questions may be added. Changes to the number of questions will affect the price of the survey according to the methodology described in section 2.10.

All questions shall be of a closed form.

All questionnaires shall include specific interviewer instructions and explanations of the unclear terms.

### Calculation of question units and length of questionnaire

Question units shall be used as a basis for the calculation of the cost of a survey, as the length of interviews varies with the structure of the question asked and with language. The calculation of the cost is described in section 2.10. Questions may be simple or complex, and can be filtered by the reply to previous questions.

The total number of question units in the questionnaire is the sum of the number of question units as calculated below for each question.

The questionnaires in section 5.1 include the determination of the number of question units.

#### Simple closed questions

The number of question units in the case of a simple closed question is one.

Example 1:

“What is the size of the last loan, of any kind, that your firm has obtained in the last two years? Answer categories: We did not take a loan, Smaller than 25,000 euro, 25,000-100,000 euro, 100,000 – 1,000,000 euro, or Over one million euro; plus Don’t know/Not applicable.”

This is 1 question unit (QU).

#### Complex questions with several items and identical categories

In the case of questions with several items and identical response categories, the number of question units is one (corresponding to the initial question) plus the number of items tested, all divided by two.

Example 2:

“For each of the following ways of financing, would you say that their availability has improved, remained unchanged or deteriorated for your firm over the past 6 months?

- Bank loans

- Trade credit

- Equity investments in your firm

- Debt securities issued

- Other”

This is (1+5)/2 = 3 question units (QU).

#### Filtered questions

Questions can be filtered by answers to previous questions. In the case of questions that have been asked in previous waves of the survey, the proportion of firms that are asked the filtered questions shall be calculated based on the average of the previous waves. The number of question units calculated as in the two previous sections shall be multiplied by this estimated proportion, with 10% margin added and rounded to the nearest five percentage points, and not exceeding 100%. In case the items in a complex question are differently filtered, the highest proportion of firms answering to any of the items shall be used for the question as a whole.

In case no comparable question exists, the calculations from the previous two (unfiltered) sub-sections 2.5.1.1.and 2.5.1.2.shall be applied.

Example 3:

Follow-up to example 1, only applicable in case a loan was obtained: “Who provided you this last loan? Answer categories: Bank, Private individual – family or friend, or Other sources.”

This question was only asked from the 51% of the firms (unweighted) who obtained a loan. Adding 10% and rounding to the nearest 5% gives 60%. The question is then counted as 0.6 QU.

### Design, update, and translation of the questionnaire

#### Questionnaire design

Most of the questionnaire already exists although changes may be introduced to it between waves, either in the wording of the questions, or the explanatory elements in accordance with the order procedure set out in the Contract. The ECB and/or the ECB may add or delete questions.

The contractor shall be responsible for designing new questions or improving existing questions in English, following instructions and/or drafts provided by the ECB and/or EC. If the contractor thinks that a particular aspect of the questionnaire cannot be used as it stands for technical or ethical reasons, it must inform the ECB and/or EC accordingly. The ECB and/or EC will then take a decision on the matter.

The design of the questionnaire shall be subject to the acceptance procedure set out in the Contract.

#### Finalisation of the questionnaire

Based on the instructions and/or draft provided, the contractor shall prepare a draft questionnaire, to be submitted to the ECB and the EC. The ECB and/or EC may make amendments, in cooperation with the contractor. Once the draft is accepted by the ECB and/or EC in accordance with the procedure set out in the Contract, the questionnaire becomes the final version.

#### Translation of the questionnaire

Depending on the countries covered by the survey, the questionnaires must be translated into all the languages used for the interviews.

Both for the ECB waves and the Common waves, versions for each of the languages used have already been prepared, and will be made available to the contractor. The contractor shall be responsible for updating, if needed, the translations due to the changes to the English questionnaire.

Careful attention shall be paid to administrative, cultural and more general language differences between territories which, in principle, use the same language (Great Britain / Ireland / Malta, Germany / Austria / Switzerland, France / Belgium / Luxembourg / Switzerland, and Belgium / Netherlands). Tenderers must describe the method they intend to use in SAFE to ensure the reliability of the adaptation of the questionnaires.

For every language other than English used for interviewing, the translations shall be produced at the national agencies by people who are very familiar with business surveys and business finance. Questions unchanged from one wave to the other in English must remain unchanged in the translation.

The translated questionnaires shall be submitted to the ECB and/or EC which shall accept the translation in accordance with the acceptance procedure set out in the Contract. Any disagreement must be cleared in writing with the translators in the national agencies, after which a final version will be established.

After each wave of the survey, the members of the network must ask their interviewers for a report on the manner in which the interviews were conducted. Comments on the way in which questions were asked and understood by respondents and proposals for improvement should also be reported, and noted in the evaluation report described in 2.8.1.5.

## Data processing: coding, cleaning, weighting

Tenderers must describe the methods that will be used by the SAFE coordination centre in order to ensure the high quality of the data submitted, for the steps of coding, cleaning, and weighting described below.

### At the level of the members of the network

The coordination centre must provide the members of the network with precise coding and data processing instructions, which are to be strictly respected.

Members of the network shall be responsible for proper coding of the raw data, data cleaning, and proper weighting of the raw sample to maximise representativeness (at national level). Tenderers must describe the methods that will be used under this Contract at the level of the members of the network to ensure a high quality and comparability of the data submitted to the coordination centre.

### At the level of the coordination centre

The coordination centre shall be responsible for any additional cleaning of data required (to be noted in the technical report for each member of the network concerned, see section 2.8). It shall also be responsible for establishing integrated data sets for analysis, including (establishment and control of) the weighting of data from each country in accordance with section 2.2, in order to produce valid weighted results for groupings of countries specified by the ECB and/or the EC. These might be, for example: EU6 (the six founding members of the European Union), EU12 (twelve first members of the European Union), EU15 (15 first members), EU27 (current members of the European Union), euro area at the time of the survey, “pre-in” countries (countries that have not adopted the euro at the time of the survey), candidate countries at the time of the survey.

### Weighting

The minimum weighting requirements are set out below:

A national marginal and intercellular weighting procedure must be carried out by all members of the network. The weighting shall be based on population data. As a minimum, economic activity (grouped), and size classes (less than 10 employees, 10 to 49, 50 to 249, 250 or more) must be introduced in the iteration process. The ECB and/or the ECB may request additional weighting requirements free of charge.

Tenderers shall, among other things, specify the weighting procedure that will be used.

For the total sample and for other results grouping countries as described in section 2.6.2, a weighting factor must be established which gives each country a sample size proportionate to the total sample size based on the number of firms in each country.

The standard procedure for comparing samples and universe shall be as follows:

- For each country surveyed, a proper universe description shall be provided. It must be based on official statistics (Eurostat or other). If this is not possible for a given country owing to a lack of such data, tenderers must explain which alternative solutions they propose and why.
The target variables shall comprise at least: size class and industry, and, if possible, the interaction between these two variables. Where the description of the universe is not possible for some of these variables, or for some of the industries covered, the ECB and the EC may decide to accept realistic estimates.

- Decisions about sampling/weighting shall normally be taken at national level. If the sampling frame and the universe descriptive statistics are homogeneous across several countries, these decisions may be allocated at the level of the coordination centre.

## Organisation and timetable

### Organisation of a wave of the SAFE by the ECB and/or the EC and the contractor

Each wave of the SAFE shall be subject of a specific contract between the ECB and/or the EC and the contractor. In the rest of the document, the “requesting institution(s)” for a wave refers to the institution (ECB and/or EC) requesting that particular wave.

The contractor shall be responsible for designing new questions (if any) or improving existing ones, following instructions and/or drafts provided by the ECB and/or the EC.

Timetables must be agreed for preparation as well as for delivery of initial and full results. Precise dates will be specified for each wave of the SAFE at least 15 calendar days before the start of fieldwork, and it will be the responsibility of both the requesting institution(s) and the contractor to respect them in accordance with the dates specified in section 5.6. The 15-day period may be reduced or extended at the ECB’s and/or the EC’s request, but not under 7 calendar days.

Once the English draft of the questionnaire is ready, the requesting institutions will have 5 calendar days to make amendments and approve the draft, conditional on the amendments.

After the English questionnaire has been approved by the requesting institutions, the contractor will have 5 calendar days to update the translations into all the languages for the countries to be covered. The requesting institutions will have 5 calendar days to approve the translation of the questionnaires.

### Organisation of the survey by the contractor

The standard timetable in section 5.6 must be completed by tenderers, and the following conditions must be met:

- The period between the approval of the translations of the questionnaire by the requesting institutions and the start of the fieldwork may not exceed 10 calendar days. In practice, since the planning of the waves will be known in advance and the questionnaire will be mostly unchanged, this period may be longer. Depending on requirements, the ECB and/or the EC may therefore decide that the fieldwork will start later.

- The fieldwork may not take longer than 30 calendar days, whether the survey is conducted by telephone or with a mixture of telephone and internet.

- The interval between completing the fieldwork and submitting the initial raw data (as described in section 2.8.1.2) may not be longer than 4 working days.

- The interval between completing the fieldwork and submitting the final raw data (as described in section 2.8.1.3) may not be longer than 10 calendar days.

- The interval between completing the fieldwork and submitting the technical report (as described in section 2.8.1.5) may not be longer than 10 calendar days.

- The interval between completing the fieldwork and submitting the initial results (volume A as described in section 2.8.1.4) may not be longer than 15 calendar days.

- The interval between completing the fieldwork and submitting the evaluation report (as described in section 2.8.1.5) may not be longer than 20 calendar days.

- The interval between completing the fieldwork and submitting all the data sheets (volume B as described in section 2.8.1.4) may not be longer than 25 calendar days.

- The interval between completing the fieldwork and submitting an analysis or summary report (as described in section 2.8.2) may not be longer than 40 calendar days.

The dates indicated by tenderers in section 5.6 will be taken into account for the award of the contract as follows: the number of days below the maximum authorised number of days will be calculated for each item and for each tenderer. The tenderer with the largest such value will be awarded the maximum number of points (5); the other tenderers will receive a number of points proportional to their value.

## Reports and documents – delivery, distribution and archiving

### Questionnaires, raw data (both initial and final), data analysis and technical report

The documents in this section must be sent to the ECB and/or the EC, depending on the specific contract.

The costs of production and delivery of the documents referred to below are included in the basic price and may not be the subject of any additional invoice.

#### Questionnaires

- Final English questionnaire for each wave

One electronic copy (Word or PDF) of each version (Common + ECB, Common + Commission, Common + ECB + Commission) to the ECB and the EC.

- National questionnaires

One electronic copy (Word or PDF) of the relevant versions (Common + ECB, Common + Commission, Common + ECB + Commission) to the ECB and the EC.

- Completed questionnaires

The members of the network or the coordination centre must store the data, made anonymous, for at least one year after the end of fieldwork, including questionnaires completed by internet. The link between the name and contact information of the firm and the data should be kept while the data are being edited and checked, for quality controls and possible re-interviewing.

#### Initial raw data

In order to allow the timeliest analysis of the data, a first delivery of raw data of all components (Common, Commission, and ECB) (see section 2.7.2) is to be made as soon as possible after fieldwork to the ECB and/or the EC, delivered by encrypted e-mail (PGP or equivalent). This version of the raw data must not include weights and information available from the sampling frame, but all variables from questions shall be coded and edited as needed. Tenderers shall indicate how they will prepare this data, in particular in terms of data editing (coherence controls, re-interviewing, verification with panel data).

#### Final raw data

An SPSS (Statistical Package for Social Sciences) working file (format *.sav) and a SAS XPORT file (format *.xpt) shall be delivered by encrypted email (PGP or equivalent) to the ECB and/or the EC, as soon as possible after fieldwork, and no later than presented in section 2.7.2.

This file shall contain all raw data collected for all countries surveyed, plus national and cross-national weighting information, as well as information available from the sampling frame as specified in section 2.2.2. User-friendly formatting is important (English variable and value labels, correct formats). The name and type of the variables is available in section 5.2.

In addition to the copies sent to the ECB and/or the EC, one copy shall be archived at the coordination centre for a minimum of two years after expiry of the contract.

#### Initial data analysis

The “initial data analyses” are tables of descriptive statistics, and are included upon specification by the ECB and/or the EC, and give rise to a specific mention in the invoice. The following tables shall be produced in that case:

- Volume A: for each question/item in the questionnaire and for all standard constructed variables, a table containing (labelled) frequencies and means or other synthetic indicators including elementary bivariate statistics describing distribution patterns of (weighted) replies for each country and for (weighted) EU results (or other total universe of the survey).

- Volume B: same as volume A, but cross-tabulated by demographic dimensions (variables starting with D in the questionnaire: size, turnover, age, industry, owner, subsidiarity) - for each country and for (weighted) EU results (or other total universe of the survey).

- On request, up to 15 additional bivariate and multivariate analyses, including filtering and definitions of subpopulations. These analyses are to be carried out in accordance with the instructions communicated by the requesting institution.

Initial data analysis must be delivered in electronic format, in Excel and PDF format, to the requesting institution. In addition, all initial analysis results shall also be archived at the coordination centre for a minimum of two years after expiry of the contract.

Examples of data for volumes A and B are included in section 5.3 and are available as an Excel file.

On the basis of these examples, tenderers must include in their bids examples showing how they would present the data in section 5.3 in the event of a study covering the 31 core and 7 supplementary countries. Data for additional countries not included in the data examples shall be based on the example countries. These documents shall combine comprehensiveness of information and readability.

#### Technical report and evaluation report

After each survey, the coordination centre shall submit a technical report and an evaluation report to the ECB and/or the EC. The reports shall contain an assessment rather than being merely descriptive. They shall be clear and readable; the ECB and/or the EC may request a redrafting in case the reports are not satisfactory. In this context, the format may be specified by the ECB and/or the EC.

- The technical report shall contain at least the following elements for each country, and where possible by size of firm (using the standard breakdowns based on the number of employees):

For telephone and/or internet interviews:

  - Number of interviews planned

  - Number of telephone numbers dialled / emails sent

  - Number of telephone numbers reached

  - Number of calls per contact (mean and median)

  - Number of firms contacted by telephone (total)

  - Number of firms in the target population (economic activity, for-profit company)

  - Number of interviews completed in full

  - Number of interviews completed in part (terminated during the interview)

  - Number of refusals and breakdown of the motives for refusal

  - Response rate (according to the AAPOR method, as applicable for business surveys)

  - Number of firms interviewed for the first time and which are recruited into the panel

For the firms participating in the panel:

  - Number of firms to be contacted based on the rotation of the panel

  - Number of telephone numbers dialled / emails sent

  - Number of telephone numbers reached

  - Number of calls per contact

  - Number of panel firms contacted by telephone (total)

  - Number of interviews completed in full

  - Number of interviews completed in part (terminated during the interview)

  - Number of refusals and main motives for refusal

  - Response rate (according to the AAPOR method, as applicable for business surveys)

  - Number of firms having reached the maximum number of interviews (as described in section 2.3).

The data provided for each country shall be as comparable as possible; the presentation and definition of each type of data (contacts, response rate, etc.) shall be identical in all countries. The report shall be sent in electronic format to the requesting institutions. Tenderers must briefly describe the structure they intend to use for the report and its content.

- The evaluation report shall give a brief and concise analysis of the progress of the survey.

Specifically, it shall mention any difficulties that arose in the course of the survey (difficulty in translating a concept, high non-response rate in a particular country, high refusal rate for particular reasons, non-participation of panel firms, question that was badly received, etc.) and, where appropriate, any recommendations for subsequent surveys. Tenderers must briefly describe the structure they intend to use for the report and its content.

The evaluation report shall also contain aspects relating to the comparison between samples and universe, such as:

- For each country surveyed, a proper universe description based on official statistics (Eurostat or other). If this is not possible for a country due to a lack of such data, an explanation of the reasons and a description of the alternative solutions proposed should be given.

- For each of the country surveyed, and for each of the target variables (size classes, economic activity), a comparison between the universe and unweighted and weighted samples in identical categories.

- A one-page listing of weighting factors for all countries, together with a brief argumentation for this choice.

- A brief evaluation summarising the solutions for sampling problems in terms of weighting and any necessary future improvements.

- Any discrepancies between the sampling/fieldwork instructions and the actual work carried out must be mentioned.

Both reports shall be subject to the acceptance procedure set out in the Contract.

### Written reports

Written reports present analysis of all the data from all the countries surveyed in the specific wave. They shall be included upon a specification by the ECB and/or the EC in the order procedure, and give rise to a specific mention in the invoice.

The reports must be written in English by someone with a fluent command of this language. They may, where appropriate, contain tables, graphs, maps or other illustrations. The cost of producing these items shall be included in the cost of the report and may not give rise to any additional invoices.

The cost of each type of written report shall be calculated as a percentage of the basic price of the specific survey wave. Basic price is understood to mean the price actually charged to the ECB and/or the EC for the survey data that are the base of the report. If the basic costs invoiced turn out to be lower than provided for in the specific contract (for example because the final questionnaire was shorter than originally planned), the final cost shall be taken into account for calculating the price of the reports referred below.

1. 	Analysis report: analysis of main findings by country and by demographic characteristics for all the questions relating to a given wave of the survey. Additional analyses might be carried out in accordance with the instructions communicated by the requesting institution (up to 15 bivariate and multivariate analyses, including filtering and definitions of subpopulations). The price of this kind of report may not exceed a maximum of 5% of the basic cost. The draft document shall be submitted to the ECB and/or the EC for approval. If the quality is not satisfactory, the ECB and/or the EC reserve the right to demand a rewrite.

2. 	Summary report: executive summary of the survey results (3-10 pages) together with a press release (1-2 pages). The price may not exceed 2% of the basic cost.

All reports must be delivered in electronic format, in Word and PDF format, to the requesting institution.

Requesting institution reserves the right to impose certain rules on the contractor for the presentation of the reports (logos, page layout etc).

By way of example, tenderers shall submit a brief analysis of the data presented in included in section 6.3 and Excel file. The analysis shall be submitted in English, 5,000 characters +/-20%, in electronic format, in Word and PDF format.

### SAFE seminar

After the first wave of the survey, and if possible before the second one, the contractor shall organise a seminar on the coordination of methodology, to be held in one of the countries of the euro area covered by the first wave of the survey and to be chosen by the contractor. The seminar shall last at least one day and the contractor shall ensure that at least one representative of each member of the network participating in the ECB waves (euro area countries excluding Slovenia, Slovakia, Cyprus, Malta, and Luxembourg) attends the seminar. Costs of this seminar shall be borne by the contractor and may not be invoiced to the ECB and/or the EC. Representatives of the ECB and the EC may possibly take part in the seminar, but at their own expense.

In the course of the third year of the contract (between waves 5 and 6), the ECB may request the contractor to organise a similar type of methodological seminar with all European Union countries.

Tenderers must outline their plans as regards the organisation and content of these seminars. They shall include with their tender an outline programme of between 1,500 and 2,000 characters, and provide a breakdown of the cost of the seminar.

### Archiving and publication

The coordination centre and the members of the network shall keep and archive at least one copy of each document relating to the data, results and reports used or produced under this contract, with the exception of completed questionnaires and/or data identifying the respondents (address, telephone number, etc.).

All the data must be kept and archived at the coordination centre for at least two years after the expiry of the contract.

The contractor shall grant all rights relating to the survey data, analyses and reports and those relating to reproduction and publication in accordance with the intellectual property rights set out in the Contract. The Contractor may not publish any document based on whole or in part upon the work undertaken under this Contract without the prior written approval of the ECB and/or the EC as set out in the Contract.

## Quality control

### Controls realised by the members of the network and the coordination centre within the framework of the SAFE

Tenderers must describe in detail the types of control envisaged and how they will ensure the quality of the services associated with the different stages at the level of the members of the network and at the central level. They must also specify the frequency of such controls.

### Controls realised by the ECB, the EC or their representatives

The ECB and/or the EC reserve the right to conduct quality checks of the surveys performed throughout the duration of the Contract, in accordance with Article 13 of the draft Contract

## Method for calculating the cost of a survey

On the basis of the sample sizes listed in section 5.4, and with the specific questionnaires used in each wave and in each component, the prices of each of the components and the variants are as follows:

ECB wave

| Country | Base sample size | Number of QU | Base price | Price for 100 interviews more or less | Price for one QU more or less per 100 interviews |
| --- | --- | --- | --- | --- | --- |
| [country] | N | Q | X | Y | Z |

Common wave

| Component | Country | Base sample size | Base number of QU | Base price | Price for 100 interviews more or less | Price for one QU more or less per 100 interviews |
| --- | --- | --- | --- | --- | --- | --- |
| [component] | [country] | N | Q | X | Y | Z |

The price of a survey is calculated as the sum of the prices for each component. The price of each component is calculated as the base price plus or minus the additional interviews, plus or minus the price for additional questions.

The full formula is:

X+(M-N)/100*Y+(P-Q)*M/100*Z

With

- X the base price (in the table above)

- Y the price for 100 interviews more or less (in the table above)

- Z the price for 1 QU more or less, per 100 interviews (in the table above)

- M the number of interviews in the survey

- N the base sample size (in the table above)

- P the number of QU in the questionnaire

- Q the base number of QU in the questionnaire (in the table above)

# Documentation for tenderers

Tenderers are informed that the existing results of the SAFE can be consulted at:

http://www.ecb.europa.eu/stats/money/surveys/sme/html/index.en.html

and

http://ec.europa.eu/enterprise/policies/finance/data/index_en.htm

# On site visits

No visits are planned.

# Additional specifications and documentation

This chapter is composed of the following sections

5.1	Questionnaires

5.2	Raw data files format

5.3	Sample data for volume tables

5.4	Sample sizes

5.5	Price tables

5.6	Timetable of the survey

## Questionnaires

### Current questionnaire for ECB waves

Total number of question units: 39.2, including 7 demographic questions.

D1. How many persons does your company currently employ in full time or part time in [YOUR COUNTRY] at all locations? PLEASE DON’T INCLUDE UNPAID FAMILY WORKERS AND FREELANCERS WORKING REGULARLY FOR YOUR COMPANY. (1QU)

[READ OUT – ONLY ONE ANSWER]

NUMERICAL ANSWER[0-999999]

[DK/NA]

[IF 0 EMPLOYEES  STOP INTERVIEW  INTERVIEW NOT VALID]

[IF NA   STOP INTERVIEW  INTERVIEW NOT VALID]

THE COMPANY MUST HAVE AT LEAST 1 EMPLOYEE BEYOND THE FOUNDER(S), IF THE FOUNDER IS THE ONLY EMPLOYEE – WE STILL CONSIDER THAT TO BE A 0 EMPLOYEE FIRM. FULL-TIME AND PART-TIME EMPLOYEES SHOULD EACH COUNT AS ONE EMPLOYEE. UNPAID FAMILY WORKERS AND EMPLOYEES WORKING LESS THAN 12 HOURS PER WEEK ARE TO BE EXCLUDED.

D2. How would you characterise your enterprise? Is it... (1QU)

[READ OUT – ONLY ONE ANSWER]

- part of a profit-oriented enterprise (e.g. subsidiary* or branch) not taking fully autonomous financial decisions	1

- an autonomous profit-oriented enterprise, making independent financial decisions **	2

- a non-profit enterprise (foundation, association, semi-government)	3

- [DK/NA]	9

* SUBSIDIARIES AND BRANCHES ARE CONTROLLED BY A PARENT COMPANY, WHICH OWNS THE MAJORITY OR ALL OF THE CAPITAL OF THESE ENTITIES. IN CONTRAST TO A BRANCH, A SUBSIDIARY IS A SEPARATE, DISTINCT LEGAL ENTITY.

** IN THE SENSE OF MAKING INDEPENDENT MANAGEMENT DECISIONS (THIS INCLUDES PARTNERSHIPS AND CO-OPERATIVES).

[IF 3 (NON-PROFIT)  STOP INTERVIEW]

D3. What is the main activity of your company? (1QU)

[READ OUT – ONLY ONE ANSWER] [NACE code will be included from the sample register file.]

- Mining	1

- Construction	2

- Manufacturing [INCLUDING ELECTRICITY, GAS AND WATER SUPPLY]	3

- Wholesale or retail trade	4

- Transport	5

- Real estate	6

- Other services to businesses or persons	7

- Agriculture [STOP INTERVIEW  INTERVIEW NOT VALID]	8

- Public Administration [STOP INTERVIEW  INTERVIEW NOT VALID]	9

- Financial services [STOP INTERVIEW  INTERVIEW NOT VALID]	10

- [None of these cases] [SPECIFY  IF RECODING NOT POSSIBLE STOP INTERVIEW  INTERVIEW NOT VALID]	11

- [DK/NA] [STOP INTERVIEW  INTERVIEW NOT VALID]	99

D4. What was the annual turnover of your company in [YOUR COUNTRY] in [LAST YEAR]?  (1QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

[For non-euro countries the amounts in euro will be converted to national currency. For Slovakia both euro and former national currency will be used.]

- Up to € 2 million	1

- More than € 2 million and up to € 10 million	2

- More than  € 10 million and up to € 50 million	3

- More than  € 50 million	4

- [DK/NA]	9

D5. In which year was your firm registered?* (1QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

NUMERICAL ANSWER (four digits, less or equal than [YEAR OF SURVEY])

[DK/NA]	9999

* In case of a past acquisition, please refer to the year when the acquiring company was registered, or, in case of a merger, of the largest company involved (in terms of employees).

D6.  Who are the owners of your firm? (1QU)

[READ OUT – ONLY ONE ANSWER POSSIBLE]

- Shareholders, as your company is listed on the stock market	1

- Family or entrepreneurs [MORE THAN ONE OWNER]	2

- Other firms or business associates	3

- Venture capital firms or business angels [INDIVIDUAL INVESTORS PROVIDING CAPITAL AND/OR KNOW-HOW TO YOUNG INNOVATIVE FIRMS]	4

- A natural person, one owner only 	5

- Other	7

- [DK/NA]	9

D6b. What is the gender of the owner/director/CEO of your firm? (1QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- Male	1

- Female	2

- [DK/NA]	9

Section 1: General information on the type and situation of the firm

Q0.  What is currently the most pressing problem your firm is facing? (1QU)

[READ OUT – ROTATE – ONLY ONE ANSWER IS POSSIBLE]

- Finding customers	1

- Competition	2

- Access to finance [EXPLAIN IF NEEDED: FINANCING OF YOUR FIRM – BANK LOANS, TRADE CREDIT, EQUITY, DEBT SECURITIES, OTHER EXTERNAL FINANCING]	3

- Costs of production or labour	4

- Availability of skilled staff or experienced managers	5

- Regulation [EUROPEAN AND NATIONAL LAWS, INDUSTRIAL REGULATIONS, ETC.]	6

- Other	7

- [DK/NA]	9

Q2. The following indicators are relevant for the income generation of your firm. Please tell me whether the following indicators have decreased, remained unchanged or increased over the past 6 months in your company? (3.5QU)

[READ OUT – ONLY ONE ANSWER PER LINE]

- Increased	1

- Remained unchanged	2

- Decreased	3

- [DK/NA]	9

- Turnover	1 2 3 9

- Labour cost (including social contributions)	1 2 3 9

- Other cost (materials, energy, other)	1 2 3 9

- Net interest expenses [= INTEREST EXPENSES MINUS INTEREST INCOME = WHAT YOU PAY IN INTEREST FOR YOUR DEBT MINUS WHAT YOU RECEIVE IN INTEREST FOR YOUR ASSETS]	1 2 3 9

- Profit [= NET INCOME AFTER TAXES]	1 2 3 9

- Profit margin [= THE DIFFERENCE BETWEEN THE SELLING PRICE AND THE COST PRICE FOR EACH UNIT]	1 2 3 9

Q3. Would you say that the amount of debt compared to the assets of your company has decreased, remained unchanged or increased over the past 6 months? (1QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- Increased	1

- Remained unchanged	2

- Decreased	3

- [NOT APPLICABLE, THE FIRM HAS NO DEBT] 	7

- [DK/NA]	9

Section 2: Financing of the firm

Q4. Turning to the financing structure of your firm, to finance normal day-to-day business operations or more specific projects or investments, you can use internal funds and external financing. For each of the following sources of financing, could you please indicate whether you used them OR NOT during the past 6 months? (6QU)

[READ OUT – ONE ANSWER PER LINE]

- Used	1

- Did not use	2

- [INSTRUMENT IS NOT APPLICABLE TO MY FIRM]	7

- [DK/NA]	9

- Internal funds [Cash or cash equivalent RESULTING FOR INSTANCE FROM savings, retained earnings, sales of assets] [ANOTHER ALTERNATIVE: CASH ACCOUNT]	1 2 7 9

- Grants or subsidised bank loan [involving support from public sources IN THE FORM OF GUARANTEES, REDUCED INTEREST RATE LOANS ETC.]	1 2 7 9

- Bank overdraft, credit line or credit cards overdraft [BANK OVERDRAFT = NEGATIVE BALANCE ON A BANK ACCOUNT WITH OR WITHOUT SPECIFIC PENALTIES; CREDIT LINE = PRE ARRANGED LOAN THAT CAN BE USED, IN FULL OR IN PART, AT DISCRETION AND WITH LIMITED ADVANCE WARNING; CREDIT CARD OVERDRAFT = NEGATIVE BALANCE ON THE CREDIT CARD]	1 2 7 9

- Bank loan (new or renewal; excluding overdraft and credit lines)	1 2 7 9

- Trade credit [= PURCHASE OF GOODS OR SERVICES WITHOUT MAKING IMMEDIATE CASH PAYMENT]  	1 2 7 9

- Other loan (e.g. from a related company or shareholders, excluding trade credit; from family and friends)	1 2 7 9

- Leasing or hire-purchase or factoring [LEASING AND HIRE-PURCHASE = OBTAINING THE USE OF A FIXED ASSET (E.G. CARS OR MACHINERY) IN EXCHANGE OF REGULAR PAYMENTS, BUT WITHOUT THE IMMEDIATE OWNERSHIP OF THE ASSET. FACTORING = SELLING YOUR INVOICES TO A FACTORING COMPANY. THIS COMPANY GETS YOUR DEBT AND HAS TO COLLECT IT. IT WILL MAKE A PROFIT BY PAYING YOU LESS CASH THAN THE FACE VALUE OF THE INVOICE. 	1 2 7 9

- Debt securities issued	1 2 7 9

- Subordinated loans, participation loans or similar financing instruments	1 2 7 9

- Equity investments in your firm [Issuance of quoted shares or unquoted equity or capital injection by external investors]	1 2 7 9

- Other	1 2 7 9

- [DID NOT USE EXTERNAL FINANCING]	1 2 7 9

[IF NONE OF THE FINANCING SOURCES IS SELECTED AS USED, PLEASE CONFIRM BY ASKING: “BASED ON THE REPLY TO THIS QUESTION, CAN YOU CONFIRM THAT YOUR FIRM HAS NOT USED ANY SOURCE OF FINANCING IN THE PAST 6 MONTHS, NEITHER INTERNAL NOR EXTERNAL?” AND RE-CODE THE CATEGORY WHERE APPROPRIATE.]

Q5.  For each of the following types of external financing, please tell me if your needs increased, remained unchanged or decreased over the past 6 months? (3QU)

[READ OUT – ONE ANSWER PER LINE]

- Increased	1

- Remained unchanged	2

- Decreased	3

- [INSTRUMENT NOT APPLICABLE TO MY FIRM] 	7

- [DK/NA]	9

- Bank loans (new or renewal; excluding overdraft and credit lines)	1 2 3 7 9

- Trade credit	1 2 3 7 9

- Equity investments in your firm	1 2 3 7 9

- Debt securities issued	1 2 3 7 9

- Other [LOAN FROM A RELATED COMPANY OR SHAREHOLDERS AND FROM FAMILY AND FRIENDS, LEASING AND FACTORING, GRANTS]	1 2 3 7 9

Q6.  For each of the following items, would you say that they have increased, decreased, or had no impact on your firm’s needs for external financing over the past 6 months? (2.5QU)

[READ OUT – ONE ANSWER PER LINE]

- Increased needs for external financing	1

- No impact on needs for external financing	2

- Decreased needs for external financing	3

- [NOT RELEVANT, DID NOT OCCUR]	7

- [DK/NA]	9

- Fixed Investment	1 2 3 7 9

- Inventories and working capital	1 2 3 7 9

- Availability of internal funds	1 2 3 7 9

[INTERVIEWER READ:] For the following item, if that has occurred during the past 6 months, please indicate if it has increased or decreased your firm's needs for external financing. [IF THE ITEM DID NOT OCCUR IN THE PAST 6 MONTHS, CODE 7 = NOT RELEVANT/DID NOT OCCUR]

- Mergers & Acquisitions and corporate restructuring	1 2 3 7 9

Q7A. For each of the following ways of financing, could you please indicate whether you applied for them over the past 6 months, or if you did not apply because you thought you would be rejected, because you had sufficient internal funds, or you did not apply for other reasons? [PROMPT IF NEEDED: Other external financing includes loans from other lenders, overdrafts, credit lines, equity or debt issuance, leasing, factoring, etc., but excludes bank loans and trade credit] (2QU)

[READ OUT – ONE ANSWER PER LINE]

- Applied	1

- Did not apply because of possible rejection	2

- Did not apply because of sufficient internal funds	3

- Did not apply for other reasons	4

- [DK/NA]	9

- Bank loan (new or renewal; excluding overdraft and credit lines)	1 2 3 4 9

- Trade credit	1 2 3 4 9

- Other external financing	1 2 3 4 9

[FILTER: FOR EACH OF THE ITEMS OF Q7A WHICH IS “APPLIED”, FILL THE RELEVANT ITEM IN Q7B]

Q7B. [COMMON] If you applied and tried to negotiate for this type of financing over the past 6 months, did you receive all the financing you requested, or only part of the financing you requested,  or only at unacceptable costs or terms and conditions so you did not take it, or you have not received anything at all? [PROMPT IF NEEDED: Other external financing includes loans from other lenders, overdrafts, credit lines, equity or debt issuance, leasing, factoring, etc., but excludes bank loans and trade credit] (filtered question: 29% of the firms replied “applied” in Q7A, filtering weight of the question 40%, 2QU unfiltered, final number of QU: 0.8 QU)

[READ OUT – ONLY ONE ANSWER PER LINE]

- Applied and got everything	1

- Applied but only got part of it	2

- Applied but refused because cost too high	3

- Applied but was rejected	4

- [DK/NA]	9

- Bank loan (new or renewal; excluding overdraft and credit lines)	1 2 3 4 9

- Trade credit	1 2 3 4 9

- Other external financing	1 2 3 4 9

Q9. For each of the following ways of financing, would you say that their availability has improved, remained unchanged or deteriorated for your firm over the past 6 months? (although the question is filtered, items a and b are asked to all firms. 3QU)

[READ OUT – ONE ANSWER PER LINE]

- Improved	1

- Remained unchanged	2

- Deteriorated	3

- [NOT APPLICABLE TO MY FIRM]	7

- [DK/NA]	9

[FILTER: ALL FIRMS. CODE 7 IS NOT TO BE USED FOR FIRMS HAVING “APPLIED” IN Q7A.a) and Q7A.b) RESPECTIVELY]

- Bank loans (new or renewal; excluding overdraft and credit lines)	1 2 3 7 9

- Trade credit	1 2 3 7 9

[FILTER: if any of Q7A.a), Q7A.b) or Q7A.c) is “applied”]

- Equity investments in your firm	1 2 3 7 9

- Debt securities issued	1 2 3 7 9

- Other  [LOAN FROM A RELATED COMPANY OR SHAREHOLDERS AND FROM FAMILY AND FRIENDS, LEASING AND FACTORING, GRANTS]	1 2 3 7 9

[FILTER: ALL FIRMS]

Q11.  [COMMON] The availability of external financing depends on various factors, which are in part related to the general economic situation, your firm-specific situation and to lenders’ attitudes. For each of the following factors, would you say that they have improved, remained unchanged or deteriorated over the past 6 months?  (4.5QU)

[READ OUT – ONE ANSWER PER LINE]

- Improved	1

- Remained unchanged	2

- Deteriorated	3

- [NOT APPLICABLE TO MY FIRM [FOR b), f), g), h)] 	7

- [DK]	9

- General economic outlook, to obtain external financing	1 2 3 9

- Access to public financial support including guarantees	1 2 3 7 9

- Your firm-specific outlook with respect to your sales and profitability or business plan, insofar as it affects the availability of external financing for you	1 2 3 9

- Your firm’s own capital	1 2 3 9

- Your firm’s credit history	1 2 3 9

[FOR THE FOLLOWING TWO ITEMS, CODE 7 IS NOT TO BE USED FOR FIRMS HAVING “APPLIED” IN Q7A.a) and Q7A.b) RESPECTIVELY]

- Willingness of banks to provide a loan	1 2 3 7 9

- Willingness of business partners to provide trade credit	1 2 3 7 9

- Willingness of investors to invest in equity or debt securities issued by firm	1 2 3 7 9

[FILTER: Q7A.a) IS APPLIED (Bank Loan)]

Q10.  [COMMON]  We will now consider the terms and conditions of the bank financing available to your firm, For each of the following items, could you please indicate whether they were increased, remained unchanged or were decreased the past 6 months? (filtered question: 29% of the firms replied “applied” in Q7A.a, filtering weight of the question 40%, 3.5QU unfiltered, final number of QU: 1.4 QU)

[READ OUT – ONE ANSWER PER LINE]

- Was increased by the bank	1

- Remained unchanged	2

- Was decreased by the bank	3

- [DK/NA]	9

Price terms and conditions:

- Level of interest rates	1 2 3 9

- Level of the cost of financing other than interest rates [CHARGES, FEES, COMMISSIONS]	1 2 3 9

Non-price terms and conditions:*

- Available size of loan or credit line	1 2 3 9

- Available maturity of the loan	1 2 3 9

- Collateral requirements [= THE SECURITY GIVEN BY THE BORROWER TO THE LENDER AS A PLEDGE FOR THE REPAYMENT OF THE LOAN]	1 2 3 9

- Other, e.g. loan covenants [= AN AGREEMENT OR STIPULATION LAID DOWN IN LOAN CONTRACTS UNDER WHICH THE BORROWER PLEDGES EITHER TO TAKE CERTAIN ACTION OR TO REFRAIN FROM TAKING CERTAIN ACTION], required guarantees, information requirements, procedures, time required for loan approval	1 2 3 9

Section 3: Future, growth and obstacles to growth

[FILTER: ALL FIRMS]

Q23. For each of the following types of financing available to your firm, could you please indicate whether you think their availability will improve, deteriorate, or remain unchanged over the next 6 months? (3.5QU)

[READ OUT – ONE ANSWER PER LINE]

- Will improve	1

- Will remain unchanged	2

- Will deteriorate	3

- [Instrument is not applicable to my firm]	7

- [DK/NA]	9

[FOR ITEMS b) AND d) BELOW, CODE 7 IS NOT TO BE USED FOR FIRMS HAVING “APPLIED” IN Q7A.a) and Q7A.b) RESPECTIVELY]

- Internal funds, for example from retained earnings and sale of assets	1 2 3 7 9

- Bank loans (new or renewal; excluding overdraft and credit lines)	1 2 3 7 9

- Equity investments in your firm	1 2 3 7 9

- Trade credit	1 2 3 7 9

- Debt securities issued	1 2 3 7 9

- Other [LOAN FROM A RELATED COMPANY OR SHAREHOLDERS AND FROM FAMILY AND FRIENDS, LEASING AND FACTORING, GRANTS]	1 2 3 7 9

### Current questionnaire for Common waves

The type of question (Common, Commission, or ECB) is indicated in brackets in the beginning of the question.

Total number of question units: 51.5, including 7 demographic questions.

D1. [COMMON] How many persons does your company currently employ in full time or part time in [YOUR COUNTRY] at all locations? PLEASE DON’T INCLUDE UNPAID FAMILY WORKERS AND FREELANCERS WORKING REGULARLY FOR YOUR COMPANY. (1QU)

[READ OUT – ONLY ONE ANSWER]

NUMERICAL ANSWER[0-999999]

[DK/NA]

[IF 0 EMPLOYEES  STOP INTERVIEW  INTERVIEW NOT VALID]

[IF NA   STOP INTERVIEW  INTERVIEW NOT VALID]

THE COMPANY MUST HAVE AT LEAST 1 EMPLOYEE BEYOND THE FOUNDER(S), IF THE FOUNDER IS THE ONLY EMPLOYEE – WE STILL CONSIDER THAT TO BE A 0 EMPLOYEE FIRM. FULL-TIME AND PART-TIME EMPLOYEES SHOULD EACH COUNT AS ONE EMPLOYEE. UNPAID FAMILY WORKERS AND EMPLOYEES WORKING LESS THAN 12 HOURS PER WEEK ARE TO BE EXCLUDED.

D2. [COMMON] How would you characterise your enterprise? Is it... (1QU)

[READ OUT – ONLY ONE ANSWER]

- part of a profit-oriented enterprise (e.g. subsidiary* or branch) not taking fully autonomous financial decisions	1

- an autonomous profit-oriented enterprise, making independent financial decisions **	2

- a non-profit enterprise (foundation, association, semi-government)	3

- [DK/NA]	9

* SUBSIDIARIES AND BRANCHES ARE CONTROLLED BY A PARENT COMPANY, WHICH OWNS THE MAJORITY OR ALL OF THE CAPITAL OF THESE ENTITIES. IN CONTRAST TO A BRANCH, A SUBSIDIARY IS A SEPARATE, DISTINCT LEGAL ENTITY.

** IN THE SENSE OF MAKING INDEPENDENT MANAGEMENT DECISIONS (THIS INCLUDES PARTNERSHIPS AND CO-OPERATIVES).

[IF 3 (NON-PROFIT)  STOP INTERVIEW]

D3. [COMMON] What is the main activity of your company? (1QU)

[READ OUT – ONLY ONE ANSWER] [NACE code will be included from the sample register file.]

- Mining	1

- Construction	2

- Manufacturing [INCLUDING ELECTRICITY, GAS AND WATER SUPPLY]	3

- Wholesale or retail trade	4

- Transport	5

- Real estate	6

- Other services to businesses or persons	7

- Agriculture [STOP INTERVIEW  INTERVIEW NOT VALID]	8

- Public Administration [STOP INTERVIEW  INTERVIEW NOT VALID]	9

- Financial services [STOP INTERVIEW  INTERVIEW NOT VALID]	10

- [None of these cases] [SPECIFY  IF RECODING NOT POSSIBLE STOP INTERVIEW  INTERVIEW NOT VALID]	11

- [DK/NA] [STOP INTERVIEW  INTERVIEW NOT VALID]	99

D4. [COMMON] What was the annual turnover of your company in [YOUR COUNTRY] in [LAST YEAR]?  (1QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- Up to € 2 million	1

- More than € 2 million and up to € 10 million	2

- More than  € 10 million and up to € 50 million	3

- More than  € 50 million	4

- [DK/NA]	9

D5. [COMMON] In which year was your firm registered?* (1QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

NUMERICAL ANSWER (four digits, less or equal than [YEAR OF SURVEY])

[DK/NA]	9999

* In case of a past acquisition, please refer to the year when the acquiring company was registered, or, in case of a merger, of the largest company involved (in terms of employees).

D6.  [COMMON] Who are the owners of your firm? (1QU)

[READ OUT – ONLY ONE ANSWER POSSIBLE]

- Shareholders, as your company is listed on the stock market	1

- Family or entrepreneurs [MORE THAN ONE OWNER]	2

- Other firms or business associates	3

- Venture capital firms or business angels [INDIVIDUAL INVESTORS PROVIDING CAPITAL AND/OR KNOW-HOW TO YOUNG INNOVATIVE FIRMS]	4

- A natural person, one owner only 	5

- Other	7

- [DK/NA]	9

D6b. [COMMON] What is the gender of the owner/director/CEO of your firm? (1QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- Male	1

- Female	2

- [DK/NA]	9

Section 1: General information on the type and situation of the firm

Q0.  [COMMON] What is currently the most pressing problem your firm is facing? (1QU)

[READ OUT – ROTATE – ONLY ONE ANSWER IS POSSIBLE]

- Finding customers	1

- Competition	2

- Access to finance [EXPLAIN IF NEEDED: FINANCING OF YOUR FIRM – BANK LOANS, TRADE CREDIT, EQUITY, DEBT SECURITIES, OTHER EXTERNAL FINANCING]	3

- Costs of production or labour	4

- Availability of skilled staff or experienced managers	5

- Regulation [EUROPEAN AND NATIONAL LAWS, INDUSTRIAL REGULATIONS, ETC.]	6

- Other	7

- [DK/NA]	9

Q1 [ENTR] During the past 12 months have you introduced…?  (2.5QU)

[READ OUT – ONE ANSWER PER LINE]

- Yes	1

- No	2

- [DK/NA]	9

- … a new or significantly improved product or service to the market	1 2 9

- … a new or significantly improved production process or method	1 2 9

- … a new organisation of management	1 2 9

- … a new way of selling your goods or services	1 2 9

Q2. [COMMON] The following indicators are relevant for the income generation of your firm. Please tell me whether the following indicators have decreased, remained unchanged or increased over the past 6 months in your company? (3.5QU)

[READ OUT – ONLY ONE ANSWER PER LINE]

- Increased	1

- Remained unchanged	2

- Decreased	3

- [DK/NA]	9

- Turnover	1 2 3 9

- Labour cost (including social contributions)	1 2 3 9

- Other cost (materials, energy, other)	1 2 3 9

- Net interest expenses [= INTEREST EXPENSES MINUS INTEREST INCOME = WHAT YOU PAY IN INTEREST FOR YOUR DEBT MINUS WHAT YOU RECEIVE IN INTEREST FOR YOUR ASSETS]	1 2 3 9

- Profit [= NET INCOME AFTER TAXES]	1 2 3 9

- Profit margin [= THE DIFFERENCE BETWEEN THE SELLING PRICE AND THE COST PRICE FOR EACH UNIT]	1 2 3 9

Q3. [COMMON] Would you say that the amount of debt compared to the assets of your company has decreased, remained unchanged or increased over the past 6 months? (1QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- Increased	1

- Remained unchanged	2

- Decreased	3

- [Not applicable, no debt] 	7

- [DK/NA]	9

Section 2: Financing of the firm

Q4. [COMMON] Turning to the financing structure of your firm, to finance normal day-to-day business operations or more specific projects or investments, you can use internal funds and external financing. For each of the following sources of financing, could you please indicate whether you used them OR NOT during the past 6 months? (6QU)

[READ OUT – ONE ANSWER PER LINE]

- Used	1

- Did not use	2

- [INSTRUMENT IS NOT APPLICABLE TO MY FIRM]	7

- [DK/NA]	9

- Internal funds [Cash or cash equivalent RESULTING FOR INSTANCE FROM savings, retained earnings, sales of assets] [ANOTHER ALTERNATIVE: CASH ACCOUNT]	1 2 7 9

- Grants or subsidised bank loan [involving support from public sources IN THE FORM OF GUARANTEES, REDUCED INTEREST RATE LOANS ETC.]	1 2 7 9

- Bank overdraft, credit line or credit cards overdraft [BANK OVERDRAFT = NEGATIVE BALANCE ON A BANK ACCOUNT WITH OR WITHOUT SPECIFIC PENALTIES; CREDIT LINE = PRE ARRANGED LOAN THAT CAN BE USED, IN FULL OR IN PART, AT DISCRETION AND WITH LIMITED ADVANCE WARNING; CREDIT CARD OVERDRAFT = NEGATIVE BALANCE ON THE CREDIT CARD]	1 2 7 9

- Bank loan (new or renewal; excluding overdraft and credit lines)	1 2 7 9

- Trade credit [= PURCHASE OF GOODS OR SERVICES WITHOUT MAKING IMMEDIATE CASH PAYMENT]  	1 2 7 9

- Other loan (e.g. from a related company or shareholders, excluding trade credit; from family and friends)	1 2 7 9

- Leasing or hire-purchase or factoring [LEASING AND HIRE-PURCHASE = OBTAINING THE USE OF A FIXED ASSET (E.G. CARS OR MACHINERY) IN EXCHANGE OF REGULAR PAYMENTS, BUT WITHOUT THE IMMEDIATE OWNERSHIP OF THE ASSET. FACTORING = SELLING YOUR INVOICES TO A FACTORING COMPANY. THIS COMPANY GETS YOUR DEBT AND HAS TO COLLECT IT. IT WILL MAKE A PROFIT BY PAYING YOU LESS CASH THAN THE FACE VALUE OF THE INVOICE. 	1 2 7 9

- Debt securities issued	1 2 7 9

- Subordinated loans, participation loans or similar financing instruments	1 2 7 9

- Equity investments in your firm [Issuance of quoted shares or unquoted equity or capital injection by external investors]	1 2 7 9

- Other	1 2 7 9

- [DID NOT USE EXTERNAL FINANCING]	1 2 7 9

[IF NONE OF THE FINANCING SOURCES IS SELECTED AS USED, PLEASE CONFIRM BY ASKING: “BASED ON THE REPLY TO THIS QUESTION, CAN YOU CONFIRM THAT YOUR FIRM HAS NOT USED ANY SOURCE OF FINANCING IN THE PAST 6 MONTHS, NEITHER INTERNAL NOR EXTERNAL?” AND RE-CODE THE CATEGORY WHERE APPROPRIATE.]

Q5. [ECB] For each of the following types of external financing, please tell me if your needs increased, remained unchanged or decreased over the past 6 months? (3QU)

[READ OUT – ONE ANSWER PER LINE]

- Increased	1

- Remained unchanged	2

- Decreased	3

- [INSTRUMENT NOT APPLICABLE TO MY FIRM] 	7

- [DK/NA]	9

- Bank loans (new or renewal; excluding overdraft and credit lines)	1 2 3 7 9

- Trade credit	1 2 3 7 9

- Equity investments in your firm	1 2 3 7 9

- Debt securities issued	1 2 3 7 9

- Other [LOAN FROM A RELATED COMPANY OR SHAREHOLDERS AND FROM FAMILY AND FRIENDS, LEASING AND FACTORING, GRANTS]	1 2 3 7 9

Q6. [ECB] For each of the following items, would you say that they have increased, decreased, or had no impact on your firm’s needs for external financing over the past 6 months? (2.5QU)

[READ OUT – ONE ANSWER PER LINE]

- Increased needs for external financing	1

- No impact on needs for external financing	2

- Decreased needs for external financing	3

- [NOT RELEVANT, DID NOT OCCUR]	7

- [DK/NA]	9

- Fixed Investment	1 2 3 7 9

- Inventories and working capital	1 2 3 7 9

- Availability of internal funds	1 2 3 7 9

[INTERVIEWER READ:] For the following item, if that has occurred during the past 6 months, please indicate if it has increased or decreased your firm's needs for external financing. [IF THE ITEM DID NOT OCCUR IN THE PAST 6 MONTHS, CODE 7 = NOT RELEVANT/DID NOT OCCUR]

- Mergers & Acquisitions and corporate restructuring	1 2 3 7 9

Q7A. [COMMON] For each of the following ways of financing, could you please indicate whether you applied for them over the past 6 months, or if you did not apply because you thought you would be rejected, because you had sufficient internal funds, or you did not apply for other reasons? [PROMPT IF NEEDED: Other external financing includes loans from other lenders, overdrafts, credit lines, equity or debt issuance, leasing, factoring, etc., but excludes bank loans and trade credit] (2QU)

[READ OUT – ONE ANSWER PER LINE]

- Applied	1

- Did not apply because of possible rejection	2

- Did not apply because of sufficient internal funds	3

- Did not apply for other reasons	4

- [DK/NA]	9

- Bank loan (new or renewal; excluding overdraft and credit lines)	1 2 3 4 9

- Trade credit	1 2 3 4 9

- Other external financing	1 2 3 4 9

[FILTER: FOR EACH OF THE ITEMS OF Q7A WHICH IS “APPLIED”, FILL THE RELEVANT ITEM IN Q7B]

Q7B. [COMMON] If you applied and tried to negotiate for this type of financing over the past 6 months, did you receive all the financing you requested, or only part of the financing you requested,  or only at unacceptable costs or terms and conditions so you did not take it, or you have not received anything at all? [PROMPT IF NEEDED: Other external financing includes loans from other lenders, overdrafts, credit lines, equity or debt issuance, leasing, factoring, etc., but excludes bank loans and trade credit] (filtered question: 29% of the firms replied “applied” in Q7A, filtering weight of the question 40%, 2QU unfiltered, final number of QU: 0.8 QU)

[READ OUT – ONLY ONE ANSWER PER LINE]

- Applied and got everything	1

- Applied but only got part of it	2

- Applied but refused because cost too high	3

- Applied but was rejected	4

- [DK/NA]	9

- Bank loan (new or renewal; excluding overdraft and credit lines)	1 2 3 4 9

- Trade credit	1 2 3 4 9

- Other external financing	1 2 3 4 9

Q9. [COMMON] For each of the following ways of financing, would you say that their availability has improved, remained unchanged or deteriorated for your firm over the past 6 months? (although the question is filtered, items a and b are asked to all firms. 3QU)

[READ OUT – ONE ANSWER PER LINE]

- Improved	1

- Remained unchanged	2

- Deteriorated	3

- [Not applicable to my firm]	7

- [DK/NA]	9

[FILTER: ALL FIRMS. CODE 7 IS NOT TO BE USED FOR FIRMS HAVING “APPLIED” IN Q7A.a) and Q7A.b) RESPECTIVELY]

- Bank loans  (new or renewal; excluding overdraft and credit lines)	1 2 3 7 9

- Trade credit	1 2 3 7 9

[FILTER: if any of Q7A.a), Q7A.b) or Q7A.c) is “applied”]

- Equity investments in your firm	1 2 3 7 9

- Debt securities issued	1 2 3 7 9

- Other  [LOAN FROM A RELATED COMPANY OR SHAREHOLDERS AND FROM FAMILY AND FRIENDS, LEASING AND FACTORING, GRANTS]	1 2 3 7 9

[FILTER: ALL FIRMS]

Q11.  [COMMON] The availability of external financing depends on various factors, which are in part related to the general economic situation, your firm-specific situation and to lenders’ attitudes. For each of the following factors, would you say that they have improved, remained unchanged or deteriorated over the past 6 months?  (4.5QU)

[READ OUT – ONE ANSWER PER LINE]

- Improved	1

- Remained unchanged	2

- Deteriorated	3

- [Not applicable / did not want to use [FOR b), f), g), h)] 	7

- [DK]	9

- General economic outlook, to obtain external financing	1 2 3 9

- Access to public financial support including guarantees	1 2 3 7 9

- Your firm-specific outlook with respect to your sales and profitability or business plan, insofar as it affects the availability of external financing for you	1 2 3 9

- Your firm’s own capital	1 2 3 9

- Your firm’s credit history	1 2 3 9

[FOR THE FOLLOWING TWO ITEMS, CODE 7 IS NOT TO BE USED FOR FIRMS HAVING “APPLIED” IN Q7A.a) and Q7A.b) RESPECTIVELY]

- Willingness of banks to provide a loan	1 2 3 7 9

- Willingness of business partners to provide trade credit	1 2 3 7 9

- Willingness of investors to invest in equity or debt securities issued by firm	1 2 3 7 9

[FILTER: Q7A.a) IS APPLIED (Bank Loan)]

Q10.  [COMMON]  We will now consider the terms and conditions of the bank financing available to your firm, For each of the following items, could you please indicate whether they were increased, remained unchanged or were decreased the past 6 months? (filtered question: 29% of the firms replied “applied” in  Q7A.a, filtering weight of the question 40%, 3.5QU unfiltered, final number of QU: 1.4 QU)

[READ OUT – ONE ANSWER PER LINE]

- Was increased by the bank	1

- Remained unchanged	2

- Was decreased by the bank	3

- [DK/NA]	9

Price terms and conditions:

- Level of interest rates	1 2 3 9

- Level of the cost of financing other than interest rates [CHARGES, FEES, COMMISSIONS]	1 2 3 9

Non-price terms and conditions:*

- Available size of loan or credit line	1 2 3 9

- Available maturity of the loan	1 2 3 9

- Collateral requirements [= THE SECURITY GIVEN BY THE BORROWER TO THE LENDER AS A PLEDGE FOR THE REPAYMENT OF THE LOAN]	1 2 3 9

- Other, e.g. loan covenants [= AN AGREEMENT OR STIPULATION LAID DOWN IN LOAN CONTRACTS UNDER WHICH THE BORROWER PLEDGES EITHER TO TAKE CERTAIN ACTION OR TO REFRAIN FROM TAKING CERTAIN ACTION], required guarantees, information requirements, procedures, time required for loan approval	1 2 3 9

[FILTER: ALL FIRMS]

Q12. [ENTR] What is the size of the last loan, of any kind, that your firm has obtained in the last two years? (1QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- We did not take a loan	1

- Smaller than 25 000 euro	2

- 25 000-100 000 euro	3

- 100 000 – 1 000 000 euro	4

- Over one million euro	5

- [DK/NA]	9

[FILTER: Q12 is 2, 3, 4, OR 5]

Q13. [ENTR] Who provided you this last loan? (filtered question: 51% of the firms replied 2, 3, 4 or 5 in Q12, filtering weight of the question 60%, 1QU unfiltered, final number of QU: 0.6 QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- Bank	1

- Private individual – family or friend	2

- Other sources (e.g. microfinance institutions, government-related sources)	3

- [DK/NA]	9

[FILTER: Q12 is 2, 3, 4, OR 5]

Q14.  [ENTR] What did you use this last loan for? (filtered question: 51% of the firms replied 2, 3, 4 or 5 in  Q12, filtering weight of the question 60%, 1QU unfiltered, final number of QU: 0.6 QU)

[READ OUT – ROTATE – SEVERAL ANSWERS POSSIBLE]

- Working capital	1

- Land/ buildings or Equipment/vehicles	2

- Research and development or intellectual property	3

- Promotion	4

- Staff training	5

- Buying another business	6

- Other	7

- [DK/NA]	9

Section 3: Future, growth and obstacles to growth

Q16. [ENTR] Over the last three years, how much did your firm grow on average per year …?  (1.5QU)

[READ OUT – ONE ANSWER PER LINE]

- Over 20% per year	1

- Less than 20% per year	2

- No growth	3

- Got smaller	4

- [Not applicable, the firm is too recent]	7

- [DK/NA,]	9

- …in terms of employment regarding the number of full time or full-time equivalent employees ?	1 2 3 4 7 9

- …and in terms of turnover?	1 2 3 4 7 9

Q17. [ENTR] Considering the turnover over the next two to three years, how much does your company expect to grow? (1QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- Grow substantially – over 20% per year in terms of turnover	1

- Grow moderately – below 20% per year in terms of turnover	2

- Stay the same size	3

- Become smaller	4

- [DK/NA]	9

Q19. [ENTR] Do you feel confident to talk about financing with banks and to obtain the desired results? And how about equity investors/ venture capital firms? (1.5QU)

[READ OUT – ONE ANSWER PER LINE]

- Yes	1

- No	2

- [Not applicable]	7

- [DK]	9

- With banks	1 2 7 9

- With equity investors/ venture capital firms	1 2 7 9

[ASK IF Q17=1 OR 2]

Q20. [ENTR] If you need external financing to realise your growth ambitions, what type of external financing would you prefer most? [Ask this and next two question if Q17 = 1 or 2 (firm expects to grow)] (filtered question: 45% of the firms replied 1 or 2 in Q17, filtering weight of the question 55%, 1QU unfiltered, final number of QU: 0.55 QU)

[READ OUT –ROTATE- ONLY ONE ANSWER IS POSSIBLE]

- Bank loan	1

- Loan from other sources (e.g. trade credit, related company, shareholder, public sources)	2

- Equity investment	3

- Subordinated loans, participation loans or similar financing instruments	4

- Other	5

- [DK/NA]	9

Q21. [ENTR] And what amount of financing would you aim to obtain? (filtered question: 45% of the firms replied 1 or 2 in Q17, filtering weight of the question 55%, 1QU unfiltered, final number of QU: 0.55 QU)

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- Less than 25 000 Euros	1

- 25 000 – 100 000 Euros	2

- 100 000 – 1 000 000 Euros	3

- Over 1 000 000 Euros	4

- [DK/NA]	9

Q22 [ENTR] What do you see as the most important limiting factor to get this financing? (filtered question: 40% of the firms replied 1 or 2, or 3 or 4 in Q20, filtering weight of the question 50%, 1QU unfiltered, final number of QU: 0.5 QU)

[ASK IF BANK OR OTHER LOAN (1 or 2 in Q20):]

A.

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- There are no obstacles	8

- Insufficient collateral or guarantee	1

- Interest rates or price too high	2

- Reduced control over the firm	3

- Financing not available at all	4

- Other	5

- [DK/NA]	9

[ASK IF EQUITY INVESTMENT OR MEZZANINE (3 OR 4 in Q20):]

B.

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- Interest rates or price too high	2

- Reduced control over the firm	3

- Financing not available at all	4

- Other	5

- [DK/NA]	9

[ASK ALL]

Q23. [ECB] For each of the following types of financing available to your firm, could you please indicate whether you think their availability will improve, deteriorate, or remain unchanged over the next 6 months? (3.5QU)

[READ OUT – ONE ANSWER PER LINE]

- Will improve	1

- Will remain unchanged	2

- Will deteriorate	3

- [Instrument is not applicable to my firm]	7

- [DK/NA]	9

[FOR ITEMS b) AND d) BELOW, CODE 7 IS NOT TO BE USED FOR FIRMS HAVING “APPLIED” IN Q7A.a) and Q7A.b) RESPECTIVELY]

- Internal funds, for example from retained earnings and sale of assets	1 2 3 7 9

- Bank loans (new or renewal; excluding overdraft and credit lines)	1 2 3 7 9

- Equity investments in your firm	1 2 3 7 9

- Trade credit	1 2 3 7 9

- Debt securities issued	1 2 3 7 9

- Other [LOAN FROM A RELATED COMPANY OR SHAREHOLDERS AND FROM FAMILY AND FRIENDS, LEASING AND FACTORING, GRANTS]	1 2 3 7 9

[ASK ONLY IF D6=2 OR 3 OR 4 OR 5 OR 6]

Q24.  [ENTR] Does your company aim to be listed on a stock market within the next 2 years? (filtered question: 90% of the firms replied 2, 3, 4, 5 or 6 in D6, filtering weight of the question 100%, 1QU unfiltered, final number of QU: 1 QU)

[Skip this and next question if ‘Who are the owners of your firm’ = ‘1’ (company is listed)]

[READ OUT – ONLY ONE ANSWER IS POSSIBLE]

- Yes, on the main list of the stock exchange	1

- Yes, on the alternative/ growth-oriented list of stock exchange	2

- No, the company is not planning to be listed	3

- [DK/NA]	9

[ASK ONLY IF D6=2 OR 3 OR 4 OR 5 OR 6]

Q25.  [ENTR] What do you see as the main obstacle for your company being listed on a stock market? (filtered question: 90% of the firms replied 2, 3, 4, 5 or 6 in D6, filtering weight of the question 100%, 1QU unfiltered, final number of QU: 1 QU)

[READ OUT – ROTATE – SEVERAL ANSWERS POSSIBLE]

- Firm is too small	1

- Listing is too expensive	2

- Reporting requirements would be too heavy	3

- Partial loss of control over time	4

- Expected market conditions are unfavourable	5

- [Other]	6

- [DK/NA]	9

## Raw data files format

The raw data files transmitted to the ECB and the EC shall contain the following variables, with the following names and codes (see sections 2.8.1.2 and 2.8.1.3).

| Variable | Type | Codes |
| --- | --- | --- |
| country | Character | Two character code of the country, ISO 3166 |
| firmid | Numerical | Unique identifier of the firm, constant across waves |
| panel | Numerical | Number of previous interviews (0 = first time) |
| mode | Numerical | Mode of survey |
| component | Numerical | 1=ECB, 2=EC, 3=Common |
| year, month, day, hour | Numerical | Date and time of survey |
| duration | Numerical | Interview duration in minutes |
| d[x] | Numerical | Questions D[x] in the questionnaire |
| d[x]_rec | Numerical | Answers provided in categories, for example number of employees (D1) |
| q[x] and q[x]_[y] | Numerical | Questions Q[x] in the questionnaire. If several items: item [y] of question Q[x] in the questionnaire |
| s_[x] | Numerical or character | Information available from the sample register: x=legal form, number of employees, turnover, sales, profit, NACE code, etc. |
| w[x] | Numerical | Weight of the firm (x=different weights for different weighting schemes) |
| o[x] | Numerical or character | Any other variable |

## Sample data for the volume tables

Data are based on the Flash Eurobarometer access to finance survey conducted in 2009.

The sample tables are also available as an Excel file [SAFE data.xls].

### Table A

### Table B

## Sample sizes

The sample sizes indicated here are the sample sizes currently being used.

### ECB waves

| Country | Base sample size |  | Country | Base sample size |
| --- | --- | --- | --- | --- |
| Austria | 200 |  | Italy | 1000 |
| Belgium | 200 |  | Luxembourg | 0 |
| Cyprus | 0 |  | Malta | 0 |
| Finland | 100 |  | Netherlands | 250 |
| France | 1000 |  | Portugal | 250 |
| Germany | 1000 |  | Slovakia | 0 |
| Greece | 200 |  | Slovenia | 0 |
| Ireland | 100 |  | Spain | 1000 |

### Common waves

| Country | Base sample size |  | Country | Base sample size |
| --- | --- | --- | --- | --- |
| Austria | 200 |  | Latvia | 100 |
| Belgium | 200 |  | Lithuania | 100 |
| Bulgaria | 200 |  | Luxembourg | 100 |
| Croatia | 100 |  | Malta | 100 |
| Cyprus | 100 |  | Netherlands | 300 |
| Czech Republic | 200 |  | Norway | 100 |
| Denmark | 200 |  | Poland | 300 |
| Estonia | 100 |  | Portugal | 300 |
| Finland | 100 |  | Romania | 200 |
| France | 1000 |  | Slovakia | 100 |
| Germany | 1000 |  | Slovenia | 100 |
| Greece | 200 |  | Spain | 1000 |
| Hungary | 200 |  | Sweden | 200 |
| Iceland | 100 |  | Turkey | 300 |
| Ireland | 100 |  | United Kingdom | 500 |
| Italy | 1000 |  |  |  |

## Price tables

This Annex must be duly filled in by the tenderers. The price tables are available as Excel files. Prices shall be fixed during the term of the Contract (four years).

### ECB waves

| Country | Base sample size | Base number of QU | Base price | Price for 100 interviews more or less | Price for one QU more or less per 100 interviews |
| --- | --- | --- | --- | --- | --- |
| Austria | 200 | 39 |  |  |  |
| Belgium | 200 | 39 |  |  |  |
| Cyprus | 100 | 39 |  |  |  |
| Finland | 100 | 39 |  |  |  |
| France | 1000 | 39 |  |  |  |
| Germany | 1000 | 39 |  |  |  |
| Greece | 200 | 39 |  |  |  |
| Ireland | 100 | 39 |  |  |  |
| Italy | 1000 | 39 |  |  |  |
| Luxembourg | 100 | 39 |  |  |  |
| Malta | 100 | 39 |  |  |  |
| Netherlands | 250 | 39 |  |  |  |
| Portugal | 250 | 39 |  |  |  |
| Slovakia | 100 | 39 |  |  |  |
| Slovenia | 100 | 39 |  |  |  |
| Spain | 1000 | 39 |  |  |  |

### Common waves

| Component | Country | Base sample size | Base number of QU | Base price | Price for 100 interviews more or less | Price for one QU more or less per 100 interviews |
| --- | --- | --- | --- | --- | --- | --- |
| Common | Austria | 200 | 51 |  |  |  |
| Common | Belgium | 200 | 51 |  |  |  |
| EC | Bulgaria | 200 | 42 |  |  |  |
| EC | Croatia | 100 | 42 |  |  |  |
| Common | Cyprus | 100 | 51 |  |  |  |
| EC | Czech Republic | 200 | 42 |  |  |  |
| EC | Denmark | 200 | 42 |  |  |  |
| EC | Estonia | 100 | 42 |  |  |  |
| Common | Finland | 100 | 51 |  |  |  |
| Common | France | 300 | 51 |  |  |  |
| ECB | France | 700 | 39 |  |  |  |
| Common | Germany | 300 | 51 |  |  |  |
| ECB | Germany | 700 | 39 |  |  |  |
| Common | Greece | 200 | 51 |  |  |  |
| EC | Hungary | 200 | 42 |  |  |  |
| EC | Iceland | 100 | 42 |  |  |  |
| Common | Ireland | 100 | 51 |  |  |  |
| Common | Italy | 300 | 51 |  |  |  |
| ECB | Italy | 700 | 39 |  |  |  |
| EC | Latvia | 100 | 42 |  |  |  |
| EC | Lithuania | 100 | 42 |  |  |  |
| Common | Luxembourg | 100 | 51 |  |  |  |
| Common | Malta | 100 | 51 |  |  |  |
| Common | Netherlands | 200 | 51 |  |  |  |
| ECB | Netherlands | 100 | 39 |  |  |  |
| EC | Norway | 100 | 42 |  |  |  |
| EC | Poland | 300 | 42 |  |  |  |
| Common | Portugal | 200 | 51 |  |  |  |
| ECB | Portugal | 100 | 39 |  |  |  |
| EC | Romania | 200 | 42 |  |  |  |
| Common | Slovakia | 100 | 51 |  |  |  |
| Common | Slovenia | 100 | 51 |  |  |  |
| Common | Spain | 300 | 51 |  |  |  |
| ECB | Spain | 700 | 39 |  |  |  |
| EC | Sweden | 200 | 42 |  |  |  |
| EC | Turkey | 300 | 42 |  |  |  |
| EC | United Kingdom | 500 | 42 |  |  |  |
| Supplementary countries |  |  |  |  |  |  |
| EC | Liechtenstein | 100 | 42 |  |  |  |
| EC | Serbia | 100 | 42 |  |  |  |
| EC | Israel | 100 | 42 |  |  |  |
| EC | Montenegro | 100 | 42 |  |  |  |
| EC | Switzerland | 100 | 42 |  |  |  |
| EC | Albania | 100 | 42 |  |  |  |
| EC | FYROM | 100 | 42 |  |  |  |

### Other items to be priced

Written reports (see section 2.8.2)

- Analytical report: percentage of the price of the survey

- Summary report: percentage of the price of the survey

SAFE seminar (see section 2.8.3): price and breakdown (for information only)

### Reference price

In order to evaluate and compare the commercial tenders, the reference price will be calculated using the formula set out in Chapter IV, section 5.4 of the ITT.

## Timetable of the survey

Annex to be filled by the tenderers according to the instructions in section 2.7, also available as an Excel file.

| Step | Starting from… | Number of days | Type of days |
| --- | --- | --- | --- |
| Start of the fieldwork | Approval of the translations of the questionnaire |  | calendar |
| End of fieldwork | Start of fieldwork |  | calendar |
| Initial raw data | End of fieldwork |  | working |
| Final raw data | End of fieldwork |  | calendar |
| Technical report | End of fieldwork |  | calendar |
| Initial results (volume A) | End of fieldwork |  | calendar |
| All data sheets (volume B) | End of fieldwork |  | calendar |
| Analysis or summary report | End of fieldwork |  | calendar |

The part of the table with the grey background represents the part of the Common waves that are to be paid by the ECB, including that the cost of the Common questions of the Common component will be split between the ECB and the EC. See section 5.5.

ECB website for the survey: http://www.ecb.europa.eu/stats/money/surveys/sme/html/index.en.html

DG Enterprise and Industry website: http://ec.europa.eu/enterprise/policies/finance/data/