## Release T2 R2024.NOV Calendar
Line | Week number | Day/ Week/ Weekend | Start Date | End Date | Activity type | Activities | EAC | UTEST | PROD | FW | Other | Comments
1 | 15 | Weeks | 2023-04-12 | 2023-10-26 | Release scope | 4CB completes CR detailed assessments/PBI feasibility assessments for baseline release scope (including cross-service impact assessments where relevant)
2 | 45 | Weeks | 2023-11-08 | 2023-11-08 | Release scope | T2-WG proposes baseline release scope and STP
3 | 46 | Weeks | 2023-11-15 | 2023-11-15 | Release scope | STP approved by the MIB | [5 empty] | Updated scope/STP to be approved
4 | 23 | Day | 2024-06-07 | 2024-06-07 | Documentation | Delivery of non-binding XSDs in MyStandards for the T2-WG community and the market | E |  |  |  |  | 8 weeks before EAC deployment (OGPF)
5 | 26 | Day | 2024-06-28 | 2024-06-28 | Release deployment | Deployment of Package 0 to EAC | E |  |  |  |  | Package 0 dedicated to CR T2-0126-SYS
6 | 29 | Day | 2024-07-19 | 2024-07-19 | Release deployment | Deployment of Package 0 to UTEST |  | U |  |  |  | Package 0 dedicated to CR T2-0126-SYS
7 | 30 | Day | 2024-07-24 | 2024-07-24 | Documentation | Publication date for binding XSDs in MyStandards for the T2-WG community and the market | E |  |  |  |  | 9 business days before EAC deployment (OGPF)
9 | 31 | Day | 2024-07-29 | 2024-07-29 | Release scope | Publication date for draft Scope defining set of documents (T2 and Common Components)
10 | 31 | Weekend | 2024-08-02 | 2024-08-02 | Release deployment | Deployment of Package 1 to EAC | E
11 | 32 | Weeks | 2024-08-05 | 2024-09-09 | Release testing | R2024.NOV Release testing (EAC) | E
12 | 33 | Weekend | 2024-08-16 | 2024-08-16 | Release deployment | Deployment of Package 2 to EAC | E
13 | 35 | Weekend | 2024-08-30 | 2024-08-30 | Release deployment | Deployment of Package 3 to EAC | E
14 | 36 | Weekend | 2024-09-06 | 2024-09-06 | Release deployment | Deployment of Package 4 to EAC | E
15 | 37 | Day | 2024-09-09 | 2024-09-09 | Reporting | Service Transition Status Report (STSR) for T2 R2024.NOV in Pre-Production (cut-off and delivery to TRSG and SMSG)
16 | 37 | Day | 2024-09-10 | 2024-09-10 | Reporting | T2-WG Go / No-go decision to deploy T2 R2024.NOV to Pre-Production | [5 empty] | 8 business days before UTEST deployment
17 | 37 | Day | 2024-09-10 | 2024-09-10 | Documentation | T2-WG/RMCG approval of the security assessment and STSR for T2 R2024.NOV in Pre-Production
18 | 37 | Day | 2024-09-11 | 2024-09-11 | Documentation | Delivery of CR Detailed Assessments to ECB Compliance Team for GDPR check | [5 empty] | This step is performed in view of the yearly reporting to the MIB in terms of GDPR by the ECB Compliance Team.
19 | 37 | Weekend | 2024-09-13 | 2024-09-13 | Release deployment | Deployment of Package 5 to EAC | E
21 | 37 | Day | 19/09/2024 | 19/09/2024 | Release deployment | Deployment of Package 6 to EAC | E
20 | 38 | Day | 2024-09-20 | 2024-09-20 | Release scope | Latest publication date for updated Scope defining set of documents (T2 and Common Components)
22 | 38 | Weekend | 2024-09-20 | 2024-09-20 | Release deployment | Deployment of Package 1, 2, 3, 4, 5 and 6 to Pre-Production |  | U
23 | 39 | Weeks | 2024-09-23 | 2024-10-30 | Release testing | R2024.NOV Release testing (UTEST) |  | U
24 | 39 | Weekend | 2024-09-27 | 2024-09-27 | Release deployment | Deployment of Package 7 to EAC and Pre-Production | E | U |  |  |  | RD only
25 | 40 | Weekend | 2024-10-04 | 2024-10-04 | Release deployment | Deployment of Package 8 to EAC and Pre-Production | E | U |  |  |  | RD only
26 | 41 | Weekend | 2024-10-11 | 2024-10-11 | Release deployment | Deployment of Package 9 to EAC and Pre-Production | E | U |  |  |  | critical RD only
27 | 42 | Weekend | 2024-10-18 | 2024-10-18 | Release deployment | Deployment of Package 10 to EAC and Pre-Production | E | U |  |  |  | critical RD only
28 | 43 | Weekend | 2024-10-25 | 2024-10-25 | Release deployment | Deployment of Package 11 to EAC and Pre-Production | E | U |  |  |  | critical RD only
29 | 44 | Day | 2024-10-30 | 2024-10-30 | Reporting | Delivery of the T2 R2024.NOV Information security assessment to RMCG
30 | 44 | Day | 2024-10-30 | 2024-10-30 | Reporting | Service Transition Status Report (STSR) for T2 R2024.NOV in Production (cut-off and delivery to TRSG and SMSG)
32 | 44 | Day | 2024-10-31 | 2024-10-31 | Reporting | T2-WG recommends the release deployment to Production |  |  | P |  |  | 11 business days before PROD deployment (OGPF)
33 | 44 | Weekend | 2024-11-01 | 2024-11-01 | Release deployment | Deployment of Package 12 to EAC and Pre-Production | E | U |  |  |  | critical RD only
34 | 45 | Day | 2024-11-05 | 2024-11-05 | Reporting | MIB approves the release deployment to Production |  |  | P |  |  | 8 business days before PROD deployment (OGPF)
31 | 45 | Day | 2024-11-08 | 2024-11-08 | Release testing | End of testing of T2 R2024.NOV scope elements in Pre-Production |  | U
35 | 46 | Weekend | 2024-11-16 | 2024-11-16 | Release deployment | Start release deployment to Production |  |  | P
Formulas:
Week number = WEEKNUM([Start Date])