## Release R2025.NOV Calendar
Line | Week number | Day/ Week/ Weekend | Start Date | End Date | Activity type | Activities | Release Milestone | EAC | UTEST | PROD | FW | Other | Comments
1 | 47 | Day | 2024-11-19 | 2024-11-19 | Release scope | T2-WG proposes baseline release scope and STP for T2 R2025.NOV
2 | 48 | Day | 2024-11-26 | 2024-11-26 | Release scope | Scope baseline & STP for T2 R2025.NOV approved by the MIB
3 | 24 | Day | 2025-06-13 | 2025-06-13 | Documentation | Delivery of non-binding XSDs in MyStandards for the T2-WG community and the market (T2 R2025.NOV) | [6 empty] | 8 weeks before EAC deployment (OGPF)
4 | 31 | Day | 2025-07-29 | 2025-07-29 | Documentation | Publication date for binding XSDs in MyStandards for the T2-WG community and the market (T2 R2025.NOV) | [6 empty] | 9 business days before EAC deployment (OGPF)
5 | 32 | Day | 2025-08-05 | 2025-08-05 | Documentation | Publication date for draft Scope defining set of documents (T2 and Common Components) related to T2 R2025.NOV
6 | 32 | Day | 2025-08-08 | 2025-08-08 | Release deployment | T2 R2025.NOV deployment (Package 1) |  | E |  |  |  |  | Proposed RN 7 business days before deployment. If no CR or XSD changes then only fiinal RN 2 business day before deployment.
10 | 33 | Week | 2025-08-11 | 2025-09-15 | Release testing | T2 R2025.NOV release testing in EAC |  | E
7 | 34 | Day | 2025-08-22 | 2025-08-22 | Release deployment | T2 R2025.NOV deployment (Package 2) |  | E |  |  |  |  | Proposed RN 7 business days before deployment. If no CR or XSD changes then only fiinal RN 2 business day before deployment.
8 | 36 | Day | 2025-09-05 | 2025-09-05 | Release deployment | T2 R2025.NOV deployment (Package 3) |  | E |  |  |  |  | Proposed RN 7 business days before deployment. If no CR or XSD changes then only fiinal RN 2 business day before deployment.
11 | 37 | Day | 2025-09-11 | 2025-09-11 | Documentation | Latest publication date for updated Scope defining set of documents (T2 and Common Components) related to T2 R2025.NOV
9 | 37 | Day | 2025-09-12 | 2025-09-12 | Release deployment | T2 R2025.NOV deployment (Package 4) |  | E |  |  |  |  | Proposed RN 7 business days before deployment. If no CR or XSD changes then only fiinal RN 2 business day before deployment.
12 | 38 | Day | 2025-09-15 | 2025-09-15 | Reporting | Service Transition Status Report (STSR) for T2 R2025.NOV in Pre-Production (cut-off and delivery to T2-WG)
13 | 38 | Day | 2025-09-16 | 2025-09-16 | Reporting | T2-WG Go / No-go decision to deploy T2 R2025.NOV to Pre-Production | [6 empty] | 8 business days before UTEST deployment
14 | 38 | Day | 2025-09-16 | 2025-09-16 | Documentation | T2-WG/RMCG approval of the security assessment and STSR for T2 R2025.NOV in Pre-Production
15 | 38 | Day | 2025-09-17 | 2025-09-17 | Documentation | Release risk assessment | [6 empty] | T2 Evolution and Operations teams are producing this assessment at the latest 8 weeks before PROD deployment
16 | 38 | Day | 2025-09-17 | 2025-09-17 | Documentation | Delivery of T2 R2025.NOV CR Detailed Assessments to ECB Compliance Team for GDPR check | [6 empty] | This step is performed in view of the yearly reporting to the MIB in terms of GDPR by the ECB Compliance Team.
17 | 38 | Day | 2025-09-18 | 2025-09-18 | Release deployment | T2 R2025.NOV deployment (Package 5) |  | E |  |  |  |  | Proposed RN 7 business days before deployment. If no CR or XSD changes then only fiinal RN 2 business day before deployment.
18 | 39 | Day | 2025-09-26 | 2025-09-26 | Release deployment | T2 R2025.NOV deployment (Package 6) |  | E |  |  |  |  | Proposed RN 7 business days before deployment. If no CR or XSD changes then only fiinal RN 2 business day before deployment.
19 | 39 | Day | 2025-09-26 | 2025-09-26 | Release deployment | Start release deployment to Pre-production |  | U
20 | 39 | Day | 2025-09-26 | 2025-09-26 | Release deployment | T2 R2025.NOV deployment to Pre-production (Packages 1-6) |  |  | U |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
21 | 40 | Day | 2025-09-29 | 2025-09-29 | Release testing | Start of testing of T2 R2025.NOV scope elements in Pre-Production |  | U
22 | 40 | Week | 2025-09-29 | 2025-11-05 | Release testing | T2 R2025.NOV release testing in Pre-Production |  |  | U
23 | 40 | Day | 2025-10-02 | 2025-10-02 | Release deployment | T2 R2025.NOV deployment (Package 7) |  | E | U |  |  |  | RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
24 | 41 | Day | 2025-10-10 | 2025-10-10 | Release deployment | T2 R2025.NOV deployment (Package 8) |  | E | U |  |  |  | RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
25 | 42 | Day | 2025-10-17 | 2025-10-17 | Release deployment | T2 R2025.NOV deployment (Package 9) |  | E | U |  |  |  | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
26 | 43 | Day | 2025-10-24 | 2025-10-24 | Release deployment | T2 R2025.NOV deployment (Package 10) |  | E | U |  |  |  | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
27 | 44 | Day | 2025-10-31 | 2025-10-31 | Release deployment | T2 R2025.NOV deployment (Package 11) |  | E | U |  |  |  | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
28 | 45 | Day | 2025-11-05 | 2025-11-05 | Release testing | End of testing of T2 R2025.NOV scope elements in Pre-Production |  |  | U
29 | 45 | Day | 2025-11-05 | 2025-11-05 | Reporting | Delivery of the T2 R2025.NOV Information security assessment to RMCG
30 | 45 | Day | 2025-11-05 | 2025-11-05 | Reporting | Service Transition Status Report (STSR) for T2 R2025.NOV in Production (cut-off and delivery to T2-WG)
31 | 45 | Day | 2025-11-06 | 2025-11-06 | Reporting | T2-WG recommends the release deployment of T2 R2025.NOV to Production | [6 empty] | 11 business days before PROD deployment (OGPF)
32 | 45 | Day | 2025-11-07 | 2025-11-07 | Release deployment | T2 R2025.NOV deployment (Package 12) |  | E | U |  |  |  | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
33 | 46 | Day | 2025-11-12 | 2025-11-12 | Reporting | MIB approves the release deployment of T2 R2025.NOV to Production | [6 empty] | 8 business days before PROD deployment (OGPF)
34 | 47 | Day | 2025-11-22 | 2025-11-22 | Release deployment | Start release deployment of T2 R2025.NOV to Production |  |  |  | P
Formulas:
Week number = WEEKNUM([Start Date])