## Intro
Status definition
Status | Definition
G | On track, or, at worst, only limited delays against our target end date with corrective measures in place to recover any such delays
Y | Target completion date will be missed, and the implementation of corrective measures will make up the lost time
R | Target completion will be missed and the implementation of corrective measures will not fully recover the lost time
X | Activity is not yet scheduled to start
T2S DCP Group
List of Open Issues
Version 20.0
Extracts from the DCPG Mandate
Mandate
The primary role of the DCPG is to track and monitor the resolution of the general concerns which are relevant to Directly Connected Parties in their capacity of future CSDs/NCBs customers.
The DCPG maintains a register of the status of these general concerns, indicating who has agreed to take what action and by when (e.g. a technical group in the T2S governance, the CSG, the NCBs and/or the MIB/DG-MIP).
The DCPG has no mandate to resolve these general concerns. Topics related to the service offering of CSDs/NCBs to their customers (including the monitoring of the ability of their customers to migrate to the T2S-enabled services) are not part of the DCPG mandate: these issues are discussed bilaterally between the CSD/NCB and its clients.
5.3 Transparency
The register of general concerns raised within the DCPG is updated on the T2S website shortly ahead and shortly after each DCPG meeting and shortly ahead of CSG/AMI-SeCo meetings. In addition to the updated register, meeting summaries will be provided to reflect the flow of discussion.
ECB-PUBLIC
18 October 2018

## OpenIssues
OPEN ISSUES
A. Open issues that are specific to DCPs/DCA Holders
B. Open issues about general implementation
Issue no. |  | Date added | Description of Issue | Priority H/M/L | Status update | Status & change | Proposed action / Assigned to | Deadline
A. Open issues – specific to DCPs/DCA Holders
B. Open issues – about general implementation
B. | 1 | 2014-06-17 | Settlement finality and Insolvency Procedures: impact of SF1/2/3 definitions over common insolvency procedures (current vs. future market practices; impacts during migration). | H | For discussion at CSG/HSG. 11/12/2014: still under discussion between CSG and T2S Board. 10/06/2015: The CSG has established a Task Force to analyse further the operational impacts of SF1/2/3 definitions, following the definition of the Collective Arrangement amongst ECB, CSDs and NCBs. 16/11/2015: The taskforce has identified a high amount of manual intervention and concluded that there was a need to change some features in T2S. Consequently three Change Requests have been proposed and sent to the CRG for assessment. Furthermore, the taskforce would be dissolved once the CRs have been approved and the OMG will execute the testing on insolvency scenarios according to the procedures as indicated in the T2S MOP. 15 June 2016: The DCPG chair asks the DCPG members on the need to request from the OMG sections of the T2S MOP that are relevant for DCPs, a letter was presented to the DCPG for approval. 13 June 2017: On-going |  | 17/02/2016: issue of insolvency procedures for the client of CSD/NCB participants to be raised again to the attention of the CSG Sept-2016: CSDs should publish Disaster Recovery procedures for their markets and/or with the T2S MOP. Furthermore, Restart-After Recover (RAD) testing should be prepared and tested with the CSDs. 29/11/2016: the CSDs should provide the relevant T2S Manual of Operational Procedures sections to their Community, especially the DCPs. 18/10/2018: The CSDs are requested to review the issue and provide a new deadline (date). | TBD, upon indications from CSDs
B. | 2 | 2014-06-17 | Settlement discipline common procedures for offending party identification; other impacts expected from CSDR SD regime. | H | 02/07/2014: The DCPG argued about the complexity of implementation and agreed that the Level 2 regulation is still unknown but should not, in any case, conflict with T2S functionalities or impose new requirements on current T2S functionalities, at least before the completion of migration. 26/11/2014: the CSG TF on insolvency procedures will report its conclusions at the December 2014 CSG meeting. 11/12/2014: on 11 December 2014 the CSG welcomed the conclusions of the taskforce. A note will be circulated among the CSDs by end-2014. 15/06/2016: continue to monitor the evolution of the CSDR Taskforce, next meeting 14 June. 18/10/2018: Harmonisation Steering Group discussions are going in the direction of T2S messages carrying this data. The HSG has prepared a handbook with the process describing the market practices to be used by specific markets. - On-going |  | 02/07/2014: DCPG to liaise with the HSG Task Force on CSDR Level II. Depending on proposals for Level 2 regulation, the DCPG may consider recommending aligning the implementation of settlement discipline measures to the T2S migration schedule. 16/11/2015: still open, pending finalization of RTS from ESMA. 17/02/2016: still in progress, following the publication by ESMA of proposed RTSs for the settlement discipline measures, which are now under review by the European Commission. The CSDs will address the topic in the next CSG and are expected to establish a taskforce to perform the analysis of possible harmonised implementation requirements in T2S by the summer of 2016. 29/11/2016: the CSDR Standard has been published as a technical standard excluding the settlement discipline standards. | TBD, waiting indications from CSDR RTS
B. | 5 | 2014-06-17 | Portfolio transfers common market practices for the efficient use of T2S functionalities in respect of passing of information between custodians. | M | 02/07/2014: HSG sent a letter to EBF proposing European-wide review by EBF. 11/12/2014: a market TF is working on the recommendations that EBF has received from the HSG. EBF is in the lead with AFME and another organisation looking after smaller banks in Europe. They are verifying that the proposal be adequate for adoption also in the other markets. The work should be concluded by the next HSG meeting (24 February 2015). 10/06/2015: the EBF TF has delivered their proposal to the HSG on 10 June 2015, which will be distributed to all national communities for validation. 18/10/2018: Harmonisation Steering Group discussions are going in the direction of T2S messages carrying this data. The HSG is preparing a handbook to include definition of a standard process and other possible market solutions. |  | 17/02/2016: The European Banking Federation’s taskforce is still currently working on this task. There will be a meeting beginning of March and the information will be delivered to the Harmonisation Steering Group. 18/10/2018 - EBF to restart the work of the Portfolio Transfer WG, to collect information for the Handbook. | TBD, waiting indications from the HSG
B. | 17 | 2018-06-14 | CSDR Penalty Mechanism DCPs should be made aware on the outcome of the T2S Penalty Mechanism stemming from the CSDR taskforce | M | 14/06/2018: the CSG approved to go forward with the work related to the T2S penalty mechanism, i.e. that the Eurosystem shall provide the service to CSDs. However, there remains strong uncertainties related to the scope of the T2S penalty mechanism, with a list of working assumptions and many questions yet to be answered by ESMA before 4CB can conduct further work (re-assessment and development), hence the timeline to implement the settlement discipline regime requirements on time remains at risk. 18/10/2018 - On-going |  | Awaiting further discussion in the CSDR TF and the CSG. | TBD, waiting indications from CSDR RTS
B. | 18 | 2018-06-14 | Cyber Resilience The DCPs welcome further participation in the Cyber Resilience Oversight Expectations (CROE) for Financial Market Infrastructures. The objective of the CROE is twofold, i) to identify the expectations from Oversight perspective on how to operationalise the CPMI/IOSCO Guidance of the Cyber Resilience of FMIS and ii) Overseers to make the identified expectations transparent to the market. | M | 14/06/2018: The work to analyse the impact of the CROE on T2S should be initiated soon and if there is a need to involve the market participants, the DCPs will be contacted. 18/10/2018 - On-going |  | DCPs are expected to be involved in the future discussion as key market player for T2S markets.

## ClosedItems
CLOSED ITEMS
A. Open issues that are specific to DCPs/DCA Holders
B. Open issues about general implementation
Issue no. |  | Date added | Description of Issue | Priority H/M/L | Status update | Status & change | Proposed action / Assigned to | Deadline
A. Open issues – specific to DCPs/DCA Holders
A. | 1 | 2014-06-17 | ECB certification Criteria and test cases are currently under discussion in the MSG and the UTSG; finalisation and publication of results still pending. | H | 02/07/2014: The info was published on 10 Feb 2014 on the T2S website (cf. Key documents – Other). | CLOSED 02/07/2014
A. | 2 | 2014-06-17 | CSD authorisation 1. Detailed criteria and test cases to be finalized. Some information provided around test cases in DCP workshop on 29 Jan 2014, but detailed and stable information still pending. 2. Test guide for CSD authorization will be provided by CSDs 6 months prior to the Community test period, i.e. 02 March 2015 for wave 1. Monte Titoli will provide the test guide around September 2014. 3. Consistent approach among CSDs in user testing (timeline, standard test cases, involvement in testing activities, DCP end-to-end testing). | H | 17/06/2014: CSDs to provide deadlines for publication of required information. 02/07/2014: There is a common set of test cases for all Eurosystem Central banks. Each CSD defines their own test cases: some CSDs will just earmark those specifically required to the DPCs; others will differentiate test cases for DCPs. - Ongoing | CLOSED 25/04/2017 | 02/07/2014: CSDs to publish relevant info on average six months before the start of the community testing phase of the respective migration wave. CBs to do the same for authorisation on the cash side. 16/09/2014: confirmed by CSDs. 10/06/2015: The CSG Chair office to ask the CSDs to share information on how they deal with authorisation for their participants (DCPs and ICPs). 16/11/2015: deadlines to be revised following the definition of a new migration plan for future MWs. 17/02/2016: Still in progress, as reminder to CSDs to publish authorization criteria and test cases within six months before the start of the community testing phase for each migration wave. 29/11/2016: whereby the CSDs should publish authorisation criteria and test cases within six months before the start of community testing. | Confirmation of DCP authorization should be given at the latest by the time when static data is “frozen” in T2S PROD prior to the migration weekend
A. | 3 | 2014-06-17 | Legal status of a DCP 1. Various issues in common across CSDs still need to be clarified (e.g. liabilities and limitations of liabilities) 2. “Technical Sender” vs “Business Sender” definitions in the T2S documentation. 3. Contractual arrangements by individual CSDs are still outstanding, urgent action required to ensure legal analysis can be concluded well before go-live. | H | 17/06/2014: Legal definitions of TS and BS in Schedule 1 of FA; to be reviewed also with reference to the operational setups. | CLOSED 16/09/2014 | 02/07/2014: CSG Chair Office to prepare a few slides for the DCPG September meeting illustrating requirements and impact in other documents – e.g. MOP, including a draft proposal for the T2S FA Schedule 1 concerning the definition of TS and BS* with the aim of creating a better understanding of which DCPs have the obligation to certify. 16/09/2014: CSG Chair office presented slides on TS and BS. * c.f. 2014-02-25 DCPs workshop, slide 14 | Beginning of September 2014
A. | 4 | 2014-06-17 | DCP readiness reporting Common template to be proposed by the CSG office. |  | 02/07/2014: In the light of the scarce interest to the harmonisation of reporting from the DCPs shown by CSDs and NCBs, the group agreed to close this point. | CLOSED 02/07/2014
A. | 5 | 2014-06-17 | DCP testing 1. Is the start of DCP testing activities dependent upon the signing of DCP-specific contracts? 2. Detailed planning around testing timeline for MW1 (and also for the other migration waves). 3. DCP’s Logistical planning during “Community Testing” (what asset lines / positions / cash need to be migrated to facilitate DCP testing). 4. DCP Volume Testing: results of decisions at UTSG and MSG. | H | Members of the DCPG are liaising with the UTSG to gather the necessary information for end-to-end volume testing resource requirements. 16/09/2014: substantially covered for wave 1; it remains yellow for subsequent migration waves. 26/02/2015: the necessary information was gathered through a written consultation at the ned of 2014. | CLOSED 26/02/2015 | 02/07/2014: DCPs to agree on strictly necessary time needed for performing end-to-end volume testing. To be considered: - number of available weekends is 24, of which 8 are already reserved for other activities; - most volumes will be in waves 3. | For migration waves after wave 1, linked to the planning of the MSG
A. | 6 | 2014-06-17 | Migration Communication: DCPs to be promptly informed on progress during Migration, discuss method of information/updates sharing. | H for wave 1 | Info during the migration weekend. The DCPG was informed that the MSG was currently working on the Migration Communication Framework which would also include the communication towards the markets participants (e.g. website for users’ community). Some DCPG members considered that the Migration Information Centre (MIC) could be expanded to provide selected information during the migration weekend even beyond CSDs and NCBs 11/12/2014: the project team confirmed that the first migration-weekend test was conducted successfully (on 21-22 November) and lessons learnt will be analysed further. | CLOSED 26/02/2015 | 02/07/2014: MSG to inform the DCPG what is planned to be provided to inform the market participants and to potentially consider, e.g. a specific section of the MIC dedicated to DCPs. T2S PO to check timeline with MSG Chair. 16/09/2014: the MSG confirmed that there will be a dedicated webpage, rather than an ad hoc session in the MIC. The MSG is still working on the detailed requirement for the communication procedures. 26/11/2014: The MSG took stock of the information requirements provided by the DCPs in a written consultation in the course of October. In its December meeting, it will decide on the classification of the necessary information. 26/02/2015: the outcome of the MSG discussion was communicated to the DCPG in February 2015. | Linked to the migration planning of the MSG
A. | 7 | 2014-06-17 | T2 Guideline amendments Work in progress at the ECB and NCBs, additional workshop planned by end of June (possible before the summer?). | H | Publication foreseen by end-2014. 11/12/2014: following discussion at the T2S Board on 10 December 2014, the draft TARGET2 Guideline is on track for submission to the ECB Governing Council for final approval in the course of January 2015. 26/02/2015: the GovC approval is now expected in March 2015 and publication in April 2015 (due to late discussion on SF1). 7/05/2015: the amending T2 Guideline was published on the ECB website on 22 April 2012. | CLOSED 07/05/2015 | ECB to organise a workshop/Info Session after summer to go through the changes introduced in the T2 Guidelines. | end-April 2015
A. | 8 | 2014-06-17 | Liquidity management and collateralization 1. Possible liquidity scenarios in different SAC-DCA-T2 PM account constellations which can benefit from T2S auto-collateralisation. 2. Provision of intraday credit to foreign branches from home NCB of HQ or local NCB of branch (remaining questions from ECB’s answers to the liquidity scenarios matrix?). 3. Interim solution for auto-collateralisation during the migration period. 4. CR for close links lists for payment banks. | H | 02/07/2014: Some dependencies from the new T2 Guideline (Issue A.7) exist. The six CBs are expected to communicate the relevant information and the details on operating instructions via the respective NUGs. 16/09/2014: the T2 Guideline is entering the approval process; GovC approval foreseen by the end of 2014; ECB suggests organising the workshop in January/February as soon as the Guideline is formally approved by the GovC. ECB ready to organise it. | CLOSED 16/09/2014 | 02/07/2014: Review against the matrix of collateralisation scenarios. Additional questions, if any, to be raised to ECB/CBs (cf. also list of DCP questions on cash and liquidity issues). 16/09/2014: the scenario matrix was reviewed. | End-September 2014
A. | 9 | 2014-06-17 | General 1. Will CSD's make available to DCP's a list of counterparty BIC's in T2S? 2. Will CSD's make available to DCP's a list of T2S accounts? | M | On-going | CLOSED 25/04/2017 | 02/07/2014: CSDs to provide information (i.e. on provision of account numbers and BICs as used in production systems). 26/02/2015: DCP BICs provided in the new DCP list. CSDs to discuss the dissemination of all conunterparties BICs and come back in the March meeting 10/06/2015: CSG to report after their next meeting as the discussion is still on-going. 17/02/2016: DCPG members reiterated the request for CSDs to provide static data information; Ms Amend reported to the DCPG that further discussions are needed between the CSDs. On-going. | asap by wave, at least a month before go-live of each wave
A. | 10 | 2014-07-10 | DCA Holders declaration Deadlines for the DCAH binding declaration should be communicated by individual NCBs. In this respect, it would be desirable to have a common approach to deadlines for binding declarations, both across migration waves and NCBs. | L |  | CLOSED 26/02/2015 | 26/11/2014: ECB T2S team to prepare a standard procedure to be adopted for adding/removing institutions to/from the official DCP list. The procedure will be discussed at the PMG in December 2014 and subsequently distributed. 26/02/2015: the procedure was approved by the PMG and communicated to the DCPG in the second half of February 2015. | 03/12/2014 (w1 U2A) 16/02/2014 (w3 A2A) 19/06/2015 (w2 U2A) 9/10/2015 (w4 A2A)
A. | 11 | 2014-07-10 | T2S Services not available in DCP mode The DCPs need to know what will be the range of services that they will be able to use as DCPs and which services will be instead available only in ICP mode. | M | On-going | CLOSED 25/04/2017 | On-going activity for all CSDs, to be explored in DCP workshops by individual CSDs. 17/02/2016: request to CSDs to provide timely updates remains on- | On-going
A. | 12 | 2014-11-26 | AML/CFT scanning according to Directive 2005/60/EC The Directive 2005/60/EC on the prevention of the use of the financial system for the purpose of money laundering and terrorist financing requires that banks scan the information before submitting settlement instructions and might have an impact on the DCP activity. | H |  | CLOSED 10/06/2015 | CSDs to investigate on implications and possible solutions. 11/12/2014: CSDs will take part in a stocktaking to tackle the matter. 10/06/2015: no action required for the time being besides what is being implemented at individual institution level. | May 2015
A. | 13 | 2017-06-13 | Definition of the T2S re-certification process for DCPs should there be a need to re-certify T2S Actors in T2S due to future releases or Change Requests. | M | The DCPG will further discuss need to re-certify T2S Actors in T2S in the next DCPG meeting in 29 November 2017. | CLOSED 16/04/2018 | The process was agreed by the DCPG in its meeting in February and apporved by the CSG in its meeting 13 April 2018. | CSG meeting April 2018
A. | 14 | 2017-10-02 | Communication enhancements between CSDs/NCBs (T2S) and DCPs/DCAHs on topics that are of specific interest for the DCPs. This need is particularly important for any planned change events (e.g. future release deployments) as well as for any unexpected situations (contingency and emergency activities). | M | The CSDs proposed to have monthly conference calls between CSDs and DCPs to discuss relevant items with the intention of optimising the communication flow and avoid any possible misunderstandings and miscommunications that could have occurred so far. The conference calls should be attended by two representatives from the DCP side, the DCPs have been asked propose a volunteer to join Mr Topa. | CLOSED 16/04/2018 | Close after meeting 16 April 2018 | end-2017
A. | 15 | 2018-06-14 | Differences in the CSD communication notes: The DCPs are requesting to have single and common communication from the CSD on the communication concerning the T2S release deployments. It is nevertheless understood that there could be local market differences that might need to be addeded to the communication, but these should be the only differences. The DCPG would request that these are clearly highlighted. | M | 14/06/2018: the issue was discussed in the DCPG meeting and the CSDs will internally discuss via the CSG Chair-Office on how to clearly highlight these discrepancies for those DCPs in multiple market. 18/10/2018: Information was sent to the relevant CSD and after further discussions with the CSG Chair-Office the issue can be closed. | CLOSED 18/10/2018 | The CSDs requested the DCPs to provide them with the actual issue of the discrepancy. The CSD where provided the differences by the DCPs after the meeting. 16/10/2018: The relevant CSD was sent the communication that triggered the discrepancy. | Earliest
B. Open issues – about general implementation
B. | 3 | 2014-06-17 | Restriction rules and MSAs* need finalization of a stable list of RRs and MSAs that will be implemented for MW1; agree timeline for final/stable lists for future MWs (relevant for x-CSD settlements as well as domestic settlements). | M | For discussion at CSG. * CSDs proposed to rename MSAs to Reference Data Extensions (RDEs). 11/12/2014: version 1.1 of the catalogue was published for all migration wave 1 CSDs. The analysis is still on-going at the X-MAP. 26/02/2015: CSDs will deliver a stable version 6 months before start of community testing. They confirmed that freezing is not possible. 16/11/2015: the CSG is assessing a proposal for future revisions to the Catalogue following the start of operations. 15/06/2016: The Catalogue of Restriction Rules version 0.5 was approved in the AG July 2016. Sept-2016: The Catalogue of Restrictions Rules version 1.0, including all the CSDs of all waves, should be prepared and sent to the HSG/AG for approval in November 2016. | CLOSED 25/04/2017 | 16/09/2014: A new version of the CSDs’ Reference Data Extension (v1.1) – formerly known as document on CSDs’Market Specific Attirbutes was already provided to the CSG. CSG Chair office to re-send it for distribution after approval at XMAP level (on-going). 23/03/2015: version 1.2.2 of the CSDs’ Reference Data Extension was shared with the DCPG on 23 March 2015. 17/02/2016: request to CSDs to provide timely updates remains on-going.
B. | 4 | 2014-06-17 | Messaging standards best practices for T2S-compliant ISO 15022 messages, SWIFT involvement in their role as standard-setting organization. |  | 02/07/2014: Exercise parked by SWIFT for insufficient resources/participation. CSDs and DCPs have a common interest in developing common best practices. However, CSDs argued that their focus until migration is on completing their internal developments by their migration wave. | CLOSED | 02/07/2014: T2S PO to see if the topic can be passed on to the HSG. Multi market DCPs to discuss whether they can get together (also with SWIFT) and put forward their own proposal.
B. | 5 | 2014-06-17 | Portfolio transfers common market practices for the efficient use of T2S functionalities in respect of passing of information between custodians. | M | 02/07/2014: HSG sent a letter to EBF proposing European-wide review by EBF. 11/12/2014: a market TF is working on the recommendations that EBF has received from the HSG. EBF is in the lead with AFME and another organisation looking after smaller banks in Europe. They are verifying that the proposal be adequate for adoption also in the other markets. The work should be concluded by the next HSG meeting (24 February 2015). 10/06/2015: the EBF TF has delivered their proposal to the HSG on 10 June 2015, which will be distributed to all national communities for validation. 16/11/2015: EBF's proposal still under review and analysis by various national communities. HSG also requested additional analysis. Sept-2016: EBF has now concluded their assessment on the topic and the proposals will now be discussed in the XMAP for compliance with harmonisation standard 4 (Interaction with T2S – Tax procedure). 13 June 2017: On-going | CLOSED 13/06/2017 | 17/02/2016: The European Banking Federation’s taskforce is still currently working on this task. There will be a meeting beginning of March and the information will be delivered to the Harmonisation Steering Group. On-going.
B. | 6 | 2014-06-17 | Market claims CASG standards vs CAJWG standards, issues re lack of agreed procedures to provide protection against counterparty risk and issuer risk. | M | For discussion at the CASG. 11/12/2014: The CASG will discuss the current findings in a conference call on 17 December 2014 and will reflect the outcome in the next update of the T2S CA standards Q&As in early 2015. | CLOSED 16/11/2015 | 16/11/2015: the CASG updated their explanations in the Q&A documentation in April 2015 (see Q1.8 and Q1.14 in https://www.ecb.europa.eu/paym/t2s/progress/pdf/subcorpact/t2s_ca_standards_faqs_october.pdf?3ba16310fa8e472caa12851235f6c99d)
B. | 7 | 2014-06-17 | Extension of EOD processes operational impacts. | M | For discussion at the CSG. 26/11/2014: change request still under discussion. CSDs seek a clearer view on the implication of the proposed changes from an operations perspective. 11/12/2014: in December 2014 the CSG approved the change request for delay of the start of night time settlement by 30 minutes to 20:00 and clarification on the T2S schedule timings. | CLOSED 26/02/2015
B. | 8 | 2014-06-17 | Timing for the opening of new accounts in case the DCP or ICP is a new member of a CSD. | M | On-going | CLOSED 13/06/2017 | 17/06/2014: CSDs to provide details on freeze period dates to the respective community. Required contractual arrangements to be discussed bilaterally. 17/02/2016: request to CSDs to provide timely updates on any freeze periods remains on-going. 29/11/2016: the CSDs of Wave 4 and Final Wave should communicate to their community, especially to the DCPs, in case there are specific requirements in relation to new securities account numbers and should there be a freeze period date for static data management before their respective migration weekends.
B. | 9 | 2014-06-23 | Primary Dealer Auctions receipt of securities issued by EU DMOs only at the home/domestic CSD, or possible in any other CSD in T2S? | L |  | CLOSED 16/11/2015 | 16/11/2015: The members of the DCPG agreed to close this open issue as no further requests for clarification were put forward.
B. | 10 | 2014-07-02 | Access rights: Non usability of cross-system entity features may create operational difficulties for DCPs |  | tem added to DCPG list (moved from the CSG Action List). 16/09/2014: the feature is available but will not be activated cross-CSDs due to the confidentiality drawbacks. 26/11/2014: CCPs’ capacity to send messages on behalf of clearing members should be clarified (context and requirements). | CLOSED | 16/09/2014: DCPs to discuss the potential drawbacks (in particular, the confidentiality issues seem to impede the use of a single file for several CSDs and to force U2A users to re-authenticate to go from one screen to the other - to be investigated). 26/11/2014: T2S team to provide information. 11/12/2014: an explanatory note was sent to the DCPG at the beginning of December 2014.
B. | 11 | 2014-07-10 | Publication of pricing CSDs should make public their pricing policy vis-à-vis their participants (both DCPs and ICPs) at least six month before the go-live of the respective migration wave. | H | On-going | CLOSED 25/04/2017 | To be discussed: information to be published by CSDs minimum 6 months before each migration phase. 16/09/2014: request acknowledged by CSDs. 17/02/2016: request to CSDs to provide timely updates on any freeze periods remains on-going.
B. | 12 | 2014-09-16 | Operational aspects Would it be possible to use collateral held outside of T2S, and If so, how would that work, and/or would transfer of that collateral into a T2S SAC be required? Some examples to be considered: i) Assets are held outside of T2S (e.g. in ICSDs, Jasdec , CREST etc.) ii) And if assets are already in T2S, are there any specific requirements re how/in which account they are kept (e.g. do they have to be in an account of the CSD appointed by the NCB)? | L | Partly answered for eurobonds by the discussion paper published on the TARGET2 website on 14 July 2014 (see also under key documents on the DCPG webpage); Non-T2S securities will work on the same basis as euro-bonds, i.e. if Eurosystem-eligible and contracts/links exist. It is up to each CSD to explain how they intend to set up this in T2S. | CLOSED 16/11/2015 | DCPs to ask CSDs. 16/11/2015: the DCPG members agree to peruse the topic by discussing the issue on a bilateral bases with the CSDs.
B. | 13 | 2014-11-26 | Info on testing activities The community should be kept up to date on the ongoing testing activities. | H | Testing reported to be going according to schedule. No specific concerns at this point. CSDs will be able to share with DCPs relevant information on identified defects. UTSG could prepare regular harmonised reporting on common issues. Release notes could also be used for this purpose , to be jointly prepared by the T2S team and the UTSG to ensure consistency across all CSDs. | CLOSED 26/02/2015 | 11/12/2014: Chair of the DCPG to attend UTSG meetings on a regular basis.
B. | 14 | 2015-03-23 | Bulk-release functionality for pending auto-collateralisation instructions: Payment banks need a bulk-release functionality in U2A to be used as back-up functionality in case A2A does not function. | M | 10/06/2015: The German NUG is in the process of preparing a CR. 15/09/2015: CR 541 "Bulk-release functionality (U2A) for settlement instructions" presented to CRG meeting on 17/18 September 2015. 15/06/2016: Change Request T2S-0541-URD (Bulk-release functionality (U2A) for settlement instructions) was put on hold for Release 2.0 potentially by the CRG meeting of 17-18 September 2015. The 4CB will provide its preliminary assessment together with other CRs on hold in the last quarter of 2016. The CRG is expected to do the scoping for the T2S Release 2.0 during the CRG meeting on 18 December 2016. Sept-2016: Remains on hold 4CB will conduct preliminary assessment from 26 Sept to17 Oct 2016. The CRG members will assign a business value indicator to all the CRs on hold (i.e. High/medium/low/not required/negative) by 18 November 2016, which will help CRG to prioritise the CRs for inclusion in future releases. | PROPSE TO CLOSE 10/10/2017 | 23/03/2015: DCPs to make further investigations. 16/11/2015: CRs proposed by the German NUG are under scrutiny. 17/02/2016: Change Request T2S-0541-URD (Bulk-release functionality (U2A) for settlement instructions) has been placed on hold and it will be considered in future releases (T2S release 2.0 or later).
B. | 15 | 2016-06-15 | T2S is producing too many messages: T2S is producing too many messages in the lifecycle of a transaction, some of which could be disregarded. | M | 16/11/2015: The DCPs should prepare a list of messages that could be stopped and provide the list to the CRG for consideration. | CLOSED 15/06/2016 | 17/02/2016: The will be a Technical Workshop concerning this topic on the 23 February 2016.
B. | 16 | 2016-06-15 | Reimbursement of pending auto-collateralisation instructions: Payment banks need a dedicated privilege for unwinding auto-collateralisation instructions, which should be segregated and allocated only to the competent teams within the banks. | H | 10/06/2015: The German NUG is in the process of preparing a CR. 15/09/2015: CR 545 "Separate release privilege for T2S auto-collateralisation reimbursement instructions" presented to CRG meeting on 17/18 September 2015. 15/06/2016: The Change Request T2S-0545-SYS (Separate release privilege for T2S auto-collateralisation reimbursement instructions) was included in R1.1.5 per CSG decision on 27 February 2016 (via written procedure). The CR was deployed in EAC on 27/05/2016, and it is planned to be delivered in MIG 2 on 17/06/2016 and in production on 26/08/2016. The Change Request T2S-0545-SYS was included in release 1.1.5 deployed on the weekend of 26-28 August 2016. | CLOSED 15/06/2016 | 23/03/2015: DCPs to make further investigations, identify potential workarounds. 16/11/2015: CRs proposed by the German NUG are under scrutiny. 17/02/2016: The DCPG members were informed that the Change Request T2S-0545-SYS (Separate release privilege for T2S auto-collateralisation reimbursement instructions), which addresses this topic, is currently part of the baseline scope for the T2S release 1.1.5. | Release 1.1.5 Agust 2016