## BIRD Work Plan 2022
Activity | Task | 2022
|  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
BIRD content | LDM / IL Review (& preliminary IReF integration) | bar: Q1 3 to Q4 11
Component design | Design proposal of logical / semantic transformation rules | bar: Q2 4 to Q3 7
IReF | CBA subgroup with banking industry & NCBs | bar: Q1 1 to Q3 7
IReF subgroup - Support to - Integration of IReF requirements into BIRD (preliminary gap analysis) – Pilot - Common country-specific requirements - Matching costs and benefits | bar: Q2 5 to Q4 12
Communication & promotion | Investigation and development of a clear strategy | bar: Q1 2 to Q2 5
Implementation of strategy and activities | bar: Q2 6 to Q4 10
Other BIRD extensions1 | Integration of Asset Encumbrance – Pilot | bar: Q2 6 to Q4 12
Refactoring of FINREP & SHSG | bar: Q3 9 to Q4 12
Work Streams (Permanent) | Work Stream on Testing's tasks
Work Stream on Data Modelling's tasks
1) These activities are initiated subject to the fact that the other activites are well-staffed and in progress.